## ROLE_TASKS
TaskId | TaskCode | TaskName | Role | Category | Stage | Description | Duration | Mandatory | PackageInteraction | WorkflowRequired | GateRelevant | KPIRelevant | Trigger | EntryCriteria | ExitCriteria | Inputs | Outputs | Approver | Consulted | Predecessor | Successor | WBS
DTL-000 | PM_01_001 | Assess project opportunity | DTL | PM_01 | ST0 | Decide whether the appointment is acceptable before mobilisation. | 2 | Y | NONE | N | N | Y | Opportunity / tender award | Appointment pack available | Go / no-go recorded | Appointment; Draft scope; Commercial outline | Opportunity decision | Client | PDM; Commercial |  | DTL-001 | PM.01.001
DTL-001 | PM_02_001 | Accept project handover | DTL | PM_02 | ST0 | Formally accept the project from the appointing party. | 1 | Y | NONE | N | N | Y | Go decision | Opportunity accepted | Handover certificate accepted | Handover pack | Accepted handover | Client | PDM; IM | DTL-000 | DTL-002 | PM.02.001
DTL-002 | PM_02_002 | Review contract and appointment | DTL | PM_02 | ST0 | Confirm contract obligations that bind DTL, PDM and IM. | 3 | Y | NONE | N | N | Y | Handover accepted | Contract issued | Contract obligations register | Contract; Appointment | Obligations register | Client | PDM; Legal | DTL-001 | DTL-003 | PM.02.002
DTL-003 | PM_02_003 | Review client requirements | DTL | PM_02 | ST0 | Confirm success criteria, constraints and interfaces. | 3 | Y | NONE | N | N | Y | Contract reviewed | Requirements pack | Requirements accepted or queried | Brief; OIR extract | Accepted requirements | Client | PDM; IM | DTL-002 | DTL-004 | PM.02.003
DTL-004 | PM_02_004 | Confirm budget envelope | DTL | PM_02 | ST0 | Confirm commercial envelope for delivery. | 2 | Y | NONE | N | N | Y | Requirements accepted | Budget issued | Budget baseline noted | Budget | Budget baseline | Client | Commercial; PDM | DTL-003 | DTL-005 | PM.02.004
DTL-005 | PM_02_005 | Confirm high-level programme | DTL | PM_02 | ST0 | Accept outline dates before detailed planning. | 2 | Y | NONE | N | N | Y | Budget noted | Outline programme | Programme envelope accepted | Outline programme | Programme envelope | Client | PDM | DTL-004 | DTL-006 | PM.02.005
DTL-006 | PM_02_006 | Review strategic risks | DTL | PM_02 | ST0 | Identify risks that block mobilisation. | 2 | Y | NONE | N | N | Y | Programme envelope | Risk workshop | Strategic risk register | Risks | Strategic risk register |  | PDM; IM | DTL-005 | DTL-007 | PM.02.006
DTL-007 | PM_02_007 | Confirm success criteria | DTL | PM_02 | ST0 | Lock measurable success criteria. | 1 | Y | NONE | N | N | Y | Risks reviewed | Criteria drafted | Success criteria approved | Requirements | Success criteria | Client | Client; PDM | DTL-006 | DTL-008 | PM.02.007
DTL-008 | PM_03_001 | Create project governance structure | DTL | PM_03 | ST0 | Seat DTL, PDM, IM and approval rights. | 2 | Y | NONE | N | N | Y | Success criteria locked | Seats named | Governance structure issued | RACI; Organisation | Governance structure | Client | PDM; IM | DTL-007 | DTL-009 | PM.03.001
DTL-009 | PM_03_002 | Appoint PDM | DTL | PM_03 | ST0 | Appoint the Project Delivery Manager. | 1 | Y | NONE | N | N | Y | Governance issued | Candidate confirmed | PDM appointed | CV / capacity | PDM appointment |  | HR; Client | DTL-008 | DTL-010 | PM.03.002
DTL-010 | PM_05_001 | Appoint Information Manager | DTL | PM_05 | ST0 | Appoint the IM. | 1 | Y | NONE | N | N | Y | PDM appointed | Candidate confirmed | IM appointed | Capacity | IM appointment |  | PDM | DTL-009 | DTL-011 | PM.05.001
DTL-011 | PM_05_002 | Confirm project team | DTL | PM_05 | ST0 | Confirm remaining delivery leadership. | 2 | Y | NONE | N | N | Y | IM appointed | Team list | Team confirmed | Organogram | Confirmed team |  | PDM | DTL-010 | DTL-012 | PM.05.002
DTL-012 | PM_05_003 | Allocate resources | DTL | PM_05 | ST0 | Allocate leadership time and key resources. | 2 | Y | NONE | N | N | Y | Team confirmed | Resource offer | Resource allocation | Capacity plan | Resource allocation |  | PDM | DTL-011 | DTL-013 | PM.05.003
DTL-013 | PM_05_004 | Establish communication structure | DTL | PM_05 | ST0 | Set reporting and escalation paths. | 1 | Y | NONE | N | N | Y | Resources allocated | Comms plan draft | Comms structure live | Stakeholders | Comms structure |  | PDM; IM | DTL-012 | DTL-014 | PM.05.004
DTL-014 | PM_05_005 | Approve project execution plan | DTL | PM_05 | ST0 | Approve PEP / delivery strategy pack. | 2 | Y | NONE | N | N | Y | PDM strategy ready | PEP submitted | PEP approved | PEP; Delivery strategy | Approved PEP | Client | PDM; IM | DTL-013;PDM-003 | DTL-015 | PM.05.005
DTL-015 | PM_05_006 | Approve mobilisation readiness | DTL | PM_05 | ST0 | Gate: no setup before this approval. | 1 | Y | NONE | N | Y | Y | PEP approved | Readiness checklist | Mobilisation approved (DTL-015) | Checklist | Mobilisation approval | Client | PDM; IM | DTL-014 | PDM-001 / IM-001 | PM.05.006
DTL-101 | PM_04_001 | Approve project governance (detailed) | DTL | PM_04 | ST1 | Approve detailed governance after PDM/IM configuration. | 2 | Y | NONE | N | N | Y | IM project configured | Governance pack | Governance approved | Governance pack | Approved governance | Client | PDM; IM | IM-001;PDM-003 | DTL-102 | PM.04.001
DTL-102 | PM_04_002 | Approve baseline programme | DTL | PM_04 | ST1 | Approve the baseline used for controls. | 2 | Y | NONE | N | N | Y | Production plan + MIDP draft | Baseline pack | Baseline approved | PDM-103; IM-101 | Baseline programme | Client | PDM; IM | PDM-103;IM-101 | DTL-103 | PM.04.002
DTL-103 | PM_04_003 | Approve resource plan | DTL | PM_04 | ST1 | Approve task-team capacity. | 2 | Y | NONE | N | N | Y | Owners assigned | Resource plan | Resource plan approved | PDM-102 | Approved resource plan | Client | PDM | PDM-102 | DTL-104 | PM.04.003
DTL-104 | PM_04_004 | Approve delivery strategy | DTL | PM_04 | ST1 | Approve how design and information will be delivered. | 2 | Y | NONE | N | N | Y | PDM strategy | Strategy pack | Strategy approved | PDM-003 | Approved delivery strategy | Client | PDM; IM | PDM-003 | DTL-105 | PM.04.004
DTL-105 | PM_04_005 | Approve MIDP | DTL | PM_04 | ST1 | Approve the master information delivery plan. | 2 | Y | NONE | N | N | Y | IM-104 complete | MIDP | MIDP approved by DTL | MIDP | Approved MIDP | Client | IM; PDM | IM-104 | DTL-201 | PM.04.005
DTL-106 | PM_04_006 | Review commercial constraints | DTL | PM_04 | ST1 | Confirm commercial limits on production. | 2 | Y | NONE | N | N | Y | Baseline in draft | Commercial note | Constraints logged | Contract | Commercial constraints |  | Commercial; PDM | DTL-102 | DTL-201 | PM.04.006
DTL-201 | PM_05_007 | Review progress reports | DTL | PM_05 | ST2 | Review PDM/IM progress at concept. | 1 | Y | NONE | N | N | Y | Concept production started | Reports issued | Comments issued | Progress reports | DTL comments |  | PDM; IM | PDM-201 | DTL-202 | PM.05.007
DTL-202 | PM_05_008 | Monitor task team performance | DTL | PM_05 | ST2 | Watch capacity and slippage. | 1 | Y | MONITOR | N | N | Y | Teams mobilised | Performance data | Actions logged | Resource plan | Performance actions |  | PDM | DTL-103 | DTL-203 | PM.05.008
DTL-203 | PM_05_009 | Manage client communication | DTL | PM_05 | ST2 | Keep the appointing party informed. | 1 | Y | NONE | N | N | Y | Ongoing | Comms calendar | Record of communication | Comms structure | Client record |  | PDM | DTL-013 | DTL-301 | PM.05.009
DTL-301 | PM_05_010 | Manage escalations | DTL | PM_05 | ST3 | Handle issues PDM cannot close. | 1 | Y | NONE | N | N | Y | Escalation raised | Issue brief | Decision recorded | Issue | Escalation decision |  | PDM; IM |  | DTL-302 | PM.05.010
DTL-302 | PM_05_011 | Review change requests | DTL | PM_05 | ST3 | Review changes with commercial impact. | 2 | Y | NONE | N | N | Y | Change raised | Change pack | Change decision | Change | Change decision | Client | PDM; Commercial |  | DTL-303 | PM.05.011
DTL-303 | PM_05_012 | Monitor multi-discipline delivery | DTL | PM_05 | ST3 | Confirm PDM is coordinating interfaces. | 1 | Y | MONITOR | N | N | Y | Packages in production | Coordination report | Oversight note | PDM-202 | Oversight note |  | PDM | PDM-202 | DTL-401 | PM.05.012
DTL-401 | PM_08_001 | Review stage-gate pack | DTL | PM_08 | ST4 | Read PDM recommendation and IM compliance. | 2 | Y | NONE | Y | Y | Y | PDM-303 and IM-303 | Gate pack | Gate pack reviewed | Gate pack | Review record |  | PDM; IM | PDM-303;IM-303 | DTL-402 | PM.08.001
DTL-402 | PM_08_002 | Approve stage gate | DTL | PM_08 | ST4 | Permit the next stage / issue. GATE. | 1 | Y | NONE | Y | Y | Y | All package approvals | Gate pack complete | Stage gate approved or rejected | All package approvals; IM compliance | Stage gate decision | Client | PDM; IM | DTL-401 | DTL-501 / IM-401 | PM.08.002
DTL-403 | PM_08_003 | Reject stage gate and return | DTL | PM_08 | ST4 | Return the stage with corrective actions. | 1 | N | NONE | Y | Y | N | Gate not ready | Findings | Rejection with actions | Findings | Corrective actions |  | PDM; IM | DTL-401 | PDM-303 | PM.08.003
DTL-501 | PM_05_013 | Approve client issue | DTL | PM_05 | ST5 | Approve information leaving the delivery team. | 1 | Y | NONE | N | N | Y | Stage gate approved | Issue pack | Client issue approved | Issue pack | Issue approval | Client | PDM; IM | DTL-402;PDM-501 | IM-401 | PM.05.013
DTL-502 | PM_05_014 | Approve construction issue | DTL | PM_05 | ST5 | Approve construction information issue. | 1 | Y | NONE | N | N | Y | Client issue path clear | C-issue pack | Construction issue approved | C-issue pack | C-issue approval |  | PDM; CM | DTL-501;PDM-502 | IM-403 | PM.05.014
DTL-601 | PM_09_001 | Monitor construction information delivery | DTL | PM_09 | ST6 | Watch that revisions keep pace with site. | 1 | Y | MONITOR | N | N | Y | On site | Revision log | Oversight actions | Registers | Oversight actions |  | PDM; IM; CM | IM-601 | DTL-602 | PM.09.001
DTL-602 | PM_09_002 | Review critical site risks | DTL | PM_09 | ST6 | Review risks that threaten safety or programme. | 1 | Y | NONE | N | N | Y | Critical risk | Risk note | Decision | Risk | Decision | Client | PDM; CM |  | DTL-603 | PM.09.002
DTL-603 | PM_09_003 | Approve major site changes | DTL | PM_09 | ST6 | Approve variations with design impact. | 2 | Y | NONE | N | N | Y | Major change | Change pack | Approval | Change | Approved change | Client | PDM; CM | PDM-603 | IM-602 | PM.09.003
DTL-604 | PM_09_004 | Manage resource conflicts | DTL | PM_09 | ST6 | Resolve capacity conflicts across teams. | 1 | Y | NONE | N | N | Y | Conflict flagged | Capacity data | Allocation decision | Resource plan | Allocation decision |  | PDM | DTL-103 | DTL-701 | PM.09.004
DTL-701 | PM_10_001 | Approve handover strategy | DTL | PM_10 | ST7 | Approve how AIM and archive will be handed over. | 2 | Y | NONE | N | N | Y | S6 complete enough | Handover strategy | Strategy approved | Strategy | Approved handover strategy | Client | PDM; IM; FM | PDM-701;IM-701 | DTL-702 | PM.10.001
DTL-702 | PM_10_002 | Review asset information readiness | DTL | PM_10 | ST7 | Confirm AIM readiness with IM. | 2 | Y | NONE | N | N | Y | Strategy approved | AIM score | Readiness accepted or rejected | AIM; AIR | Readiness view |  | IM; PDM | IM-702 | DTL-703 | PM.10.002
DTL-703 | PM_10_003 | Review final deliverables | DTL | PM_10 | ST7 | Accept the handover set. | 2 | Y | NONE | N | N | Y | AIM reviewed | Final register | Final deliverables accepted | Registers | Acceptance | Client | PDM; IM | DTL-702 | DTL-704 | PM.10.003
DTL-704 | PM_11_001 | Approve project close-out | DTL | PM_11 | ST7 | Close the delivery appointment. | 2 | Y | CLOSE | N | N | Y | Deliverables accepted | Close-out pack | Close-out approved | Close-out pack | Close-out approval | Client | PDM; IM | DTL-703 | DTL-705 | PM.11.001
DTL-705 | PM_11_002 | Lessons learned | DTL | PM_11 | ST7 | Capture delivery lessons. | 1 | Y | NONE | N | N | Y | Close-out approved | Workshop | Lessons record | Issues log | Lessons |  | PDM; IM | DTL-704 | DTL-706 | PM.11.002
DTL-706 | PM_11_003 | Performance review | DTL | PM_11 | ST7 | Review DTL/PDM/IM performance. | 1 | Y | NONE | N | N | Y | Lessons captured | KPIs | Performance note | KPIs | Performance note |  | PDM; IM | DTL-705 | DTL-707 | PM.11.003
DTL-707 | PM_11_004 | Project closure approval | DTL | PM_11 | ST7 | Formal closure. | 1 | Y | NONE | N | N | Y | Performance reviewed | Closure pack | Project closed | Pack | Closure | Client | Client | DTL-706 | DTL-708 | PM.11.004
DTL-708 | PM_11_005 | Archive approval | DTL | PM_11 | ST7 | Approve IM archive lock. | 1 | Y | CLOSE | N | N | Y | Closure approved | Archive pack | Archive approved | IM-703 | Archive approval |  | IM | IM-703 | DTL-709 | PM.11.005
DTL-709 | PM_11_006 | Operations transition | DTL | PM_11 | ST7 | Confirm FM / operator has the AIM. | 2 | Y | NONE | N | N | Y | Archive approved | AIM accepted by FM | Operations accepted | AIM | Operations acceptance | Client | FM; IM | DTL-708 | — | PM.11.006
DTL-X0601 | PM_06_001 | Review fee and cash-flow constraints | DTL | PM_06 | ST1 | Confirm commercial limits on production sequence. | 1 | Y | NONE | N | N | Y | Commercial work is open | Commercial predecessor complete | Review fee and cash-flow constraints recorded | Project record | Review fee and cash-flow constraints record | Client | PDM |  | Next task in this category | PM.06.001
DTL-X0602 | PM_06_002 | Review insurance and liability positions | DTL | PM_06 | ST1 | Confirm delivery team cover. | 1 | Y | NONE | N | N | Y | Commercial work is open | Commercial predecessor complete | Review insurance and liability positions recorded | Project record | Review insurance and liability positions record | Client | PDM |  | Next task in this category | PM.06.002
DTL-X0603 | PM_06_003 | Log provisional sums affecting packages | DTL | PM_06 | ST1 | Flag packages tied to provisional sums. | 1 | Y | NONE | N | N | Y | Commercial work is open | Commercial predecessor complete | Log provisional sums affecting packages recorded | Project record | Log provisional sums affecting packages record | Client | PDM |  | Next task in this category | PM.06.003
DTL-X0604 | PM_06_004 | Review variation authority limits | DTL | PM_06 | ST1 | Confirm who may approve what value. | 1 | Y | NONE | N | N | Y | Commercial work is open | Commercial predecessor complete | Review variation authority limits recorded | Project record | Review variation authority limits record | Client | PDM |  | Next task in this category | PM.06.004
DTL-X0701 | PM_05_015 | Approve information protocol addendum | DTL | PM_05 | ST1 | Approve IM protocol changes. | 1 | Y | NONE | N | N | Y | Governance work is open | Governance predecessor complete | Approve information protocol addendum recorded | Project record | Approve information protocol addendum record | Client | PDM |  | Next task in this category | PM.05.015
DTL-X0702 | PM_05_016 | Approve meeting cadence | DTL | PM_05 | ST1 | Lock design / IM / client cadence. | 1 | Y | NONE | N | N | Y | Governance work is open | Governance predecessor complete | Approve meeting cadence recorded | Project record | Approve meeting cadence record | Client | PDM |  | Next task in this category | PM.05.016
DTL-X0703 | PM_08_004 | Approve delegated authorities | DTL | PM_08 | ST1 | Lock PDM/IM spend and issue limits. | 1 | Y | NONE | Y | Y | Y | Governance work is open | Governance predecessor complete | Approve delegated authorities recorded | Project record | Approve delegated authorities record | Client | PDM |  | Next task in this category | PM.08.004
DTL-X0704 | PM_05_017 | Review conflict-of-interest declarations | DTL | PM_05 | ST1 | Keep governance clean. | 1 | Y | NONE | N | N | Y | Governance work is open | Governance predecessor complete | Review conflict-of-interest declarations recorded | Project record | Review conflict-of-interest declarations record | Client | PDM |  | Next task in this category | PM.05.017
DTL-X0501 | PM_05_018 | Review look-ahead (4 week) | DTL | PM_05 | ST3 | Read PDM look-ahead. | 1 | Y | NONE | N | N | Y | Oversight work is open | Oversight predecessor complete | Review look-ahead (4 week) recorded | Project record | Review look-ahead (4 week) record | Client | PDM |  | Next task in this category | PM.05.018
DTL-X0502 | PM_05_019 | Review critical-path slippage | DTL | PM_05 | ST3 | Act if critical path moves. | 1 | Y | NONE | N | N | Y | Oversight work is open | Oversight predecessor complete | Review critical-path slippage recorded | Project record | Review critical-path slippage record | Client | PDM |  | Next task in this category | PM.05.019
DTL-X0503 | PM_05_020 | Review health and safety design risk | DTL | PM_05 | ST3 | CD / residual risk oversight. | 1 | Y | NONE | N | N | Y | Oversight work is open | Oversight predecessor complete | Review health and safety design risk recorded | Project record | Review health and safety design risk record | Client | PDM |  | Next task in this category | PM.05.020
DTL-X0504 | PM_05_021 | Review stakeholder commitments | DTL | PM_05 | ST3 | Track promises to client. | 1 | Y | NONE | N | N | Y | Oversight work is open | Oversight predecessor complete | Review stakeholder commitments recorded | Project record | Review stakeholder commitments record | Client | PDM |  | Next task in this category | PM.05.021
DTL-X0801 | PM_08_005 | Confirm gate attendees | DTL | PM_08 | ST4 | Gate cannot run without quorum. | 1 | Y | NONE | Y | Y | Y | Stage Gates work is open | Stage Gates predecessor complete | Confirm gate attendees recorded | Project record | Confirm gate attendees record | Client | PDM |  | Next task in this category | PM.08.005
DTL-X0802 | PM_08_006 | Issue gate minutes | DTL | PM_08 | ST4 | Formal record of DTL-402. | 1 | Y | NONE | Y | Y | Y | Stage Gates work is open | Stage Gates predecessor complete | Issue gate minutes recorded | Project record | Issue gate minutes record | Client | PDM |  | Next task in this category | PM.08.006
DTL-X0803 | PM_05_022 | Set conditions of approval | DTL | PM_05 | ST4 | Conditional gate if used. | 1 | Y | NONE | N | N | Y | Stage Gates work is open | Stage Gates predecessor complete | Set conditions of approval recorded | Project record | Set conditions of approval record | Client | PDM |  | Next task in this category | PM.05.022
DTL-X1001 | PM_05_023 | Confirm operator training complete | DTL | PM_05 | ST7 | Operations transition evidence. | 1 | Y | NONE | N | N | Y | Handover work is open | Handover predecessor complete | Confirm operator training complete recorded | Project record | Confirm operator training complete record | Client | PDM |  | Next task in this category | PM.05.023
DTL-X1002 | PM_05_024 | Confirm spare-parts / O&M receipt | DTL | PM_05 | ST7 | Physical handover evidence. | 1 | Y | NONE | N | N | Y | Handover work is open | Handover predecessor complete | Confirm spare-parts / O&M receipt recorded | Project record | Confirm spare-parts / O&M receipt record | Client | PDM |  | Next task in this category | PM.05.024
PDM-000 | DM_02_001 | Prepare to receive the project | PDM | DM_02 | ST0 | Ready the PDM seat before DTL-015. | 1 | Y | NONE | N | N | Y | DTL-009 appointment | Appointment letter | PDM ready | Appointment | Readiness |  | DTL | DTL-009 | PDM-001 | DM.02.001
PDM-001 | DM_02_002 | Receive project | PDM | DM_02 | ST0 | Receive the project after mobilisation approval. | 1 | Y | NONE | N | N | Y | DTL-015 | Mobilisation approved | Project received on PDM register | Handover; PEP | Received project |  | DTL; IM | DTL-015 | PDM-002 | DM.02.002
PDM-002 | DM_01_001 | Review contract requirements | PDM | DM_01 | ST0 | Extract delivery obligations. | 3 | Y | NONE | N | N | Y | Project received | Contract | Obligations list | Contract | Delivery obligations |  | DTL | PDM-001 | PDM-003A | DM.01.001
PDM-003A | DM_01_002 | Review client requirements | PDM | DM_01 | ST0 | Extract design and information needs. | 3 | Y | NONE | N | N | Y | Obligations listed | Brief | Client requirements note | Brief | Requirements note |  | DTL; IM | PDM-002 | PDM-003B | DM.01.002
PDM-003B | DM_01_003 | Review OIR | PDM | DM_01 | ST0 | Read organisational information requirements. | 2 | Y | NONE | N | N | Y | Requirements note | OIR | OIR implications | OIR | OIR implications |  | IM | PDM-003A | PDM-003C | DM.01.003
PDM-003C | DM_01_004 | Review PIR | PDM | DM_01 | ST0 | Read project information requirements. | 2 | Y | NONE | N | N | Y | OIR reviewed | PIR | PIR implications | PIR | PIR implications |  | IM | PDM-003B | PDM-003D | DM.01.004
PDM-003D | DM_01_005 | Review EIR | PDM | DM_01 | ST0 | Read exchange information requirements. | 2 | Y | NONE | N | N | Y | PIR reviewed | EIR | EIR implications | EIR | EIR implications |  | IM | PDM-003C | PDM-003 | DM.01.005
PDM-003 | DM_03_001 | Create delivery strategy | PDM | DM_03 | ST0 | Define how the job will be delivered. | 3 | Y | NONE | N | N | Y | OIR/PIR/EIR reviewed | Strategy draft | Delivery strategy issued | OIR; PIR; EIR; Contract | Delivery strategy | DTL | DTL; IM | PDM-003D | IM-001 / DTL-014 | DM.03.001
PDM-004 | DM_03_002 | Create design strategy | PDM | DM_03 | ST0 | Define design management approach. | 2 | Y | NONE | N | N | Y | Delivery strategy | Design strategy draft | Design strategy issued | Delivery strategy | Design strategy | DTL | DTL; TTM | PDM-003 | PDM-005 | DM.03.002
PDM-005 | DM_02_003 | Establish design governance | PDM | DM_02 | ST0 | Set design authority and interfaces. | 2 | Y | NONE | N | N | Y | Design strategy | Governance draft | Design governance live | RACI | Design governance |  | DTL; IM | PDM-004 | PDM-101 | DM.02.003
PDM-101 | DM_05_001 | Create scope packages | PDM | DM_05 | ST1 | Identify all scope production packages. | 4 | Y | CREATE | N | N | Y | Delivery strategy approved | Package rules | Scope Package Register | FB; Ss; Teams | Scope Package Register |  | IM; TTM | PDM-003 | PDM-102 / IM-101 | DM.05.001
PDM-102 | DM_05_002 | Assign package ownership | PDM | DM_05 | ST1 | Assign each package to a task team. | 2 | Y | PLAN | N | N | Y | Register exists | Team capacity | Package owners | Register; Teams | Ownership matrix | DTL | TTM; DTL | PDM-101 | PDM-103 | DM.05.002
PDM-103 | DM_04_001 | Create production plan | PDM | DM_04 | ST1 | Sequence packages and interfaces. | 4 | Y | CREATE | N | N | Y | Owners assigned | Dependencies | Production programme | Ownership; Programme envelope | Production plan | DTL | IM; TTM | PDM-102 | PDM-104 | DM.04.001
PDM-104 | DM_08_001 | Release packages for production | PDM | DM_08 | ST1 | Release only after MIDP approval. | 2 | Y | PLAN | N | N | Y | IM-104 and DTL-102 | Release checklist | Packages released (PLANNED→ready) | MIDP; Production plan | Release record | DTL | IM; TTM | IM-104;PDM-103;DTL-102 | PKG-REL | DM.08.001
PDM-105 | DM_06_001 | Identify task teams | PDM | DM_06 | ST1 | Confirm which disciplines are required. | 2 | Y | NONE | N | N | Y | Strategy exists | Discipline list | Task team list | Scope | Task team list |  | DTL | PDM-003 | PDM-102 | DM.06.001
PDM-106 | DM_05_003 | Confirm design scope | PDM | DM_05 | ST1 | Confirm FB / systems in and out. | 3 | Y | NONE | N | N | Y | Teams listed | FB / Ss | Confirmed design scope | FB; Ss | Confirmed scope |  | IM; TTM | PDM-105 | PDM-101 | DM.05.003
PDM-107 | DM_04_002 | Review production dependencies | PDM | DM_04 | ST1 | Review package-to-package dependencies. | 2 | Y | NONE | N | N | Y | Plan drafted | Interface list | Dependency register | Packages | Dependency register |  | TTM; IM | PDM-103 | PDM-104 | DM.04.002
PDM-108 | DM_04_003 | Review delivery risks | PDM | DM_04 | ST1 | Risks to production sequence. | 2 | Y | NONE | N | N | Y | Dependencies known | Risks | Delivery risk register | Plan | Delivery risks |  | DTL | PDM-107 | PDM-201 | DM.04.003
PDM-109 | DM_06_002 | Approve production responsibilities | PDM | DM_06 | ST1 | Lock who produces, reviews, approves. | 1 | Y | NONE | N | N | Y | Owners assigned | RACI | Responsibilities approved | RACI | Approved responsibilities | DTL | DTL; IM | PDM-102 | PDM-104 | DM.06.002
PDM-201 | DM_07_001 | Monitor package progress | PDM | DM_07 | ST2 | Continuous SS with package production. | 1 | Y | MONITOR | N | N | Y | Packages released | Status feed | Progress view | Package status | Progress view |  | TTM; IM | PDM-104 | PDM-202 | DM.07.001
PDM-202 | DM_07_002 | Coordinate design interfaces | PDM | DM_07 | ST2 | SS with production. | 1 | Y | NONE | N | N | Y | Production live | Interfaces | Interface actions | Dependencies | Interface actions |  | TTM | PDM-201 | PDM-203 | DM.07.002
PDM-203 | DM_07_003 | Resolve coordination issues | PDM | DM_07 | ST2 | Triggered by clash, late deliverable or missing information. | 1 | Y | NONE | N | N | Y | Issue raised | Issue | Closed issue or escalation | Clash / late / missing | Resolution |  | TTM; IM; DTL |  | DTL-301 if needed | DM.07.003
PDM-204 | DM_06_003 | Mobilise task teams for concept | PDM | DM_06 | ST2 | Stand teams up for concept packages. | 2 | Y | NONE | N | N | Y | PDM-104 | Teams | Teams mobilised | Owners | Mobilisation record |  | TTM; DTL | PDM-104 | PDM-201 | DM.06.003
PDM-205 | DM_07_004 | Review concept package readiness | PDM | DM_07 | ST2 | Concept outputs ready for review. | 2 | Y | REVIEW | Y | N | Y | Concept produced | Concept set | Readiness note | Concept deliverables | Readiness |  | TTM; IM | PKG-PRODUCE | PDM-301 | DM.07.004
PDM-301 | DM_10_001 | Review package readiness | PDM | DM_10 | ST3 | FS after TTM approval. | 2 | Y | REVIEW | Y | N | Y | PKG-TTM | TTM approval | Readiness reviewed | TTM approval; Deliverables | Readiness review |  | TTM; IM | PKG-TTM | PDM-302 | DM.10.001
PDM-302 | DM_10_002 | Approve package | PDM | DM_10 | ST3 | Approve the package for IM publication path. | 1 | Y | APPROVE | Y | N | Y | Readiness reviewed | Review record | Package APPROVED | Readiness | Package approval | DTL | IM; DTL | PDM-301 | IM-401 / PKG-IM | DM.10.002
PDM-303 | DM_10_003 | Recommend stage gate | PDM | DM_10 | ST4 | Recommend gate only when all in-scope packages are approved. | 2 | Y | NONE | Y | Y | Y | All PDM-302 complete | Approvals register | Gate recommendation | All package approvals | Recommendation |  | IM; DTL | PDM-302 | DTL-401 | DM.10.003
PDM-304 | DM_08_002 | Review discipline progress | PDM | DM_08 | ST3 | Review each task team against the plan. | 1 | Y | NONE | N | N | Y | Production | Progress | Actions | TIDP | Actions |  | TTM | PDM-201 | PDM-305 | DM.08.002
PDM-305 | DM_07_005 | Review interface risks | PDM | DM_07 | ST3 | Review remaining interface risk. | 1 | Y | NONE | N | N | Y | Coordination live | Risks | Updated risks | Interfaces | Updated risks |  | TTM | PDM-202 | PDM-306 | DM.07.005
PDM-306 | DM_07_006 | Review scope gaps | PDM | DM_07 | ST3 | Find missing packages or systems. | 2 | Y | NONE | N | N | Y | Register vs model | Gap list | Gap actions | Register | Gap actions |  | IM; TTM | PDM-101 | PDM-307 | DM.07.006
PDM-307 | DM_07_007 | Review scope overlaps | PDM | DM_07 | ST3 | Find double-owned scope. | 1 | Y | NONE | N | N | Y | Ownership matrix | Overlap list | Ownership corrections | Ownership | Corrections |  | TTM | PDM-102 | PDM-308 | DM.07.007
PDM-308 | DM_09_001 | Review deliverable quality | PDM | DM_09 | ST3 | Sample deliverable quality. | 2 | Y | NONE | N | N | Y | Deliverables issued | Samples | Quality note | Deliverables | Quality note |  | TTM; IM | PKG-PRODUCE | PDM-301 | DM.09.001
PDM-309 | DM_09_002 | Review information completeness | PDM | DM_09 | ST3 | Completeness vs IR / LOIN. | 1 | Y | NONE | N | N | Y | IM completeness view | IR | Completeness note | IM-202 | Completeness note |  | IM | IM-202 | PDM-301 | DM.09.002
PDM-310 | DM_08_003 | Review compliance dashboards | PDM | DM_08 | ST3 | Read IM compliance. | 1 | Y | NONE | N | N | Y | Dashboards | Compliance | Actions | IM-202 | Actions |  | IM | IM-202 | PDM-303 | DM.08.003
PDM-401 | DM_10_004 | Issue corrective actions | PDM | DM_10 | ST4 | If gate rejected. | 2 | N | NONE | N | N | N | DTL-403 | Rejection | Corrective actions issued | Rejection | Actions |  | TTM; IM | DTL-403 | PDM-301 | DM.10.004
PDM-402 | DM_10_005 | Re-submit stage gate | PDM | DM_10 | ST4 | Re-submit after corrections. | 2 | N | NONE | Y | Y | N | Actions closed | Updated pack | New recommendation | Actions | Updated recommendation |  | IM; DTL | PDM-401 | DTL-401 | DM.10.005
PDM-501 | DM_10_006 | Approve design / client submissions | PDM | DM_10 | ST5 | Approve what goes to the client. | 1 | Y | NONE | N | N | Y | DTL-402 | Submission pack | Submission approved | Pack | Approval | DTL | IM | DTL-402;PDM-302 | DTL-501 | DM.10.006
PDM-502 | DM_10_007 | Approve construction issue packages | PDM | DM_10 | ST5 | Approve C-issue content. | 1 | Y | APPROVE | Y | N | Y | Client path clear | C-pack | C-issue approved | C-pack | Approval | DTL | CM; IM | PDM-501 | DTL-502 | DM.10.007
PDM-503 | DM_10_008 | Approve information releases | PDM | DM_10 | ST5 | Approve IM publication set. | 1 | Y | ASSIGN | N | N | Y | Containers ready | Release list | Release approved | IM list | Release approval |  | IM | IM-401 | IM-403 | DM.10.008
PDM-601 | DM_09_003 | Review design queries / RFIs | PDM | DM_09 | ST6 | Answer or route RFIs. | 1 | Y | NONE | N | N | Y | RFI | RFI | Response or escalation | RFI | Response |  | TTM; IM; CM |  | PDM-602 | DM.09.003
PDM-602 | DM_09_004 | Review site changes | PDM | DM_09 | ST6 | Review site-led change. | 1 | Y | NONE | N | N | Y | Site change | Change | Instruction | Change | Instruction |  | CM; DTL | PDM-601 | PDM-603 | DM.09.004
PDM-603 | DM_09_005 | Review design deviations | PDM | DM_09 | ST6 | Review deviations from issued information. | 2 | Y | NONE | N | N | Y | Deviation | Deviation | Accept / reject | Deviation | Decision | DTL | TTM; DTL | PDM-602 | PDM-604 | DM.09.005
PDM-604 | DM_10_009 | Approve revisions | PDM | DM_10 | ST6 | Approve the revised package. | 1 | Y | NONE | N | N | Y | Revision produced | Rev pack | Revision approved | Rev | Approval | DTL | IM; DTL | PKG-PRODUCE | IM-602 | DM.10.009
PDM-701 | DM_09_006 | Review handover deliverables | PDM | DM_09 | ST7 | Review the handover set. | 3 | Y | NONE | N | N | Y | S6 stable | Handover register | Review note | Register | Review |  | IM; DTL | PDM-302 | PDM-702 | DM.09.006
PDM-702 | DM_09_007 | Review AIM readiness | PDM | DM_09 | ST7 | Review AIM with IM. | 2 | Y | NONE | N | N | Y | IM-702 | AIM | AIM view | AIM | AIM view |  | IM | IM-702 | PDM-703 | DM.09.007
PDM-703 | DM_09_008 | Review asset information | PDM | DM_09 | ST7 | Review asset-level completeness. | 2 | Y | NONE | N | N | Y | AIM view | Assets | Asset note | Assets | Asset note |  | IM; FM | PDM-702 | PDM-704 | DM.09.008
PDM-704 | DM_10_010 | Approve design completion | PDM | DM_10 | ST7 | Approve that design delivery is complete. | 2 | Y | NONE | N | N | Y | Handover reviewed | Completion pack | Design completion approved | Pack | Approval | DTL | DTL; IM | PDM-701;PDM-703 | DTL-704 | DM.10.010
PDM-X0401 | DM_08_004 | Set package priorities | PDM | DM_08 | ST1 | Priority 1/2/3 on the register. | 1 | Y | NONE | N | N | Y | Production Planning work is open | Production Planning predecessor complete | Set package priorities recorded | Project record | Set package priorities record | DTL | DTL; IM |  | Next task in this category | DM.08.004
PDM-X0402 | DM_08_005 | Set package stage windows | PDM | DM_08 | ST1 | StageStart / StageEnd per package. | 1 | Y | NONE | N | N | Y | Production Planning work is open | Production Planning predecessor complete | Set package stage windows recorded | Project record | Set package stage windows record | DTL | DTL; IM |  | Next task in this category | DM.08.005
PDM-X0403 | DM_08_006 | Define look-ahead rhythm | PDM | DM_08 | ST1 | Weekly look-ahead rule. | 1 | Y | NONE | N | N | Y | Production Planning work is open | Production Planning predecessor complete | Define look-ahead rhythm recorded | Project record | Define look-ahead rhythm record | DTL | DTL; IM |  | Next task in this category | DM.08.006
PDM-X0404 | DM_08_007 | Define earned-progress rule | PDM | DM_08 | ST1 | How package % complete is measured. | 1 | Y | NONE | N | N | Y | Production Planning work is open | Production Planning predecessor complete | Define earned-progress rule recorded | Project record | Define earned-progress rule record | DTL | DTL; IM |  | Next task in this category | DM.08.007
PDM-X0405 | DM_08_008 | Define float policy | PDM | DM_08 | ST1 | Who may consume float. | 1 | Y | NONE | N | N | Y | Production Planning work is open | Production Planning predecessor complete | Define float policy recorded | Project record | Define float policy record | DTL | DTL; IM |  | Next task in this category | DM.08.008
PDM-X0406 | DM_09_009 | Define lag defaults for reviews | PDM | DM_09 | ST1 | Peer/TTIM/TTM/PDM lag days. | 1 | Y | NONE | N | N | Y | Production Planning work is open | Production Planning predecessor complete | Define lag defaults for reviews recorded | Project record | Define lag defaults for reviews record | DTL | DTL; IM |  | Next task in this category | DM.09.009
PDM-X0501 | DM_08_009 | Split combined packages | PDM | DM_08 | ST1 | Split if a package hides two assets. | 1 | Y | NONE | N | N | Y | Scope Package Planning work is open | Scope Package Planning predecessor complete | Split combined packages recorded | Project record | Split combined packages record | DTL | DTL; IM |  | Next task in this category | DM.08.009
PDM-X0502 | DM_08_010 | Merge duplicate packages | PDM | DM_08 | ST1 | Merge double-counted Ss. | 1 | Y | NONE | N | N | Y | Scope Package Planning work is open | Scope Package Planning predecessor complete | Merge duplicate packages recorded | Project record | Merge duplicate packages record | DTL | DTL; IM |  | Next task in this category | DM.08.010
PDM-X0503 | DM_08_011 | Tag package Uniclass Ss | PDM | DM_08 | ST1 | Every package has Ss. | 1 | Y | NONE | N | N | Y | Scope Package Planning work is open | Scope Package Planning predecessor complete | Tag package Uniclass Ss recorded | Project record | Tag package Uniclass Ss record | DTL | DTL; IM |  | Next task in this category | DM.08.011
PDM-X0504 | DM_08_012 | Tag package FB | PDM | DM_08 | ST1 | Every package has FB. | 1 | Y | NONE | N | N | Y | Scope Package Planning work is open | Scope Package Planning predecessor complete | Tag package FB recorded | Project record | Tag package FB record | DTL | DTL; IM |  | Next task in this category | DM.08.012
PDM-X0505 | DM_08_013 | Tag package spatial set | PDM | DM_08 | ST1 | Package knows which levels. | 1 | Y | NONE | N | N | Y | Scope Package Planning work is open | Scope Package Planning predecessor complete | Tag package spatial set recorded | Project record | Tag package spatial set record | DTL | DTL; IM |  | Next task in this category | DM.08.013
PDM-X0506 | DM_08_014 | Record package procurement type | PDM | DM_08 | ST1 | Design / design-and-construct / supply. | 1 | Y | NONE | N | N | Y | Scope Package Planning work is open | Scope Package Planning predecessor complete | Record package procurement type recorded | Project record | Record package procurement type record | DTL | DTL; IM |  | Next task in this category | DM.08.014
PDM-X0507 | DM_08_015 | Record package lead discipline | PDM | DM_08 | ST1 | Owner role code. | 1 | Y | NONE | N | N | Y | Scope Package Planning work is open | Scope Package Planning predecessor complete | Record package lead discipline recorded | Project record | Record package lead discipline record | DTL | DTL; IM |  | Next task in this category | DM.08.015
PDM-X0508 | DM_07_008 | Record package interfaces | PDM | DM_07 | ST1 | Named interface list. | 1 | Y | NONE | N | N | Y | Scope Package Planning work is open | Scope Package Planning predecessor complete | Record package interfaces recorded | Project record | Record package interfaces record | DTL | DTL; IM |  | Next task in this category | DM.07.008
PDM-X0509 | DM_08_016 | Record package hold points | PDM | DM_08 | ST1 | Hold points before produce. | 1 | Y | NONE | N | N | Y | Scope Package Planning work is open | Scope Package Planning predecessor complete | Record package hold points recorded | Project record | Record package hold points record | DTL | DTL; IM |  | Next task in this category | DM.08.016
PDM-X0510 | DM_08_017 | Record package information forms | PDM | DM_08 | ST1 | Model / drawing / schedule / spec. | 1 | Y | NONE | N | N | Y | Scope Package Planning work is open | Scope Package Planning predecessor complete | Record package information forms recorded | Project record | Record package information forms record | DTL | DTL; IM |  | Next task in this category | DM.08.017
PDM-X0601 | DM_06_004 | Confirm TTM named per team | PDM | DM_06 | ST2 | Named human for each team. | 1 | Y | NONE | N | N | Y | Task Team Coordination work is open | Task Team Coordination predecessor complete | Confirm TTM named per team recorded | Project record | Confirm TTM named per team record | DTL | DTL; IM |  | Next task in this category | DM.06.004
PDM-X0602 | DM_06_005 | Confirm TTIM named per team | PDM | DM_06 | ST2 | Named information lead. | 1 | Y | NONE | N | N | Y | Task Team Coordination work is open | Task Team Coordination predecessor complete | Confirm TTIM named per team recorded | Project record | Confirm TTIM named per team record | DTL | DTL; IM |  | Next task in this category | DM.06.005
PDM-X0603 | DM_06_006 | Confirm peer reviewer named | PDM | DM_06 | ST2 | Named PR. | 1 | Y | NONE | N | N | Y | Task Team Coordination work is open | Task Team Coordination predecessor complete | Confirm peer reviewer named recorded | Project record | Confirm peer reviewer named record | DTL | DTL; IM |  | Next task in this category | DM.06.006
PDM-X0604 | DM_06_007 | Confirm author capacity | PDM | DM_06 | ST2 | IA hours vs package duration. | 1 | Y | NONE | N | N | Y | Task Team Coordination work is open | Task Team Coordination predecessor complete | Confirm author capacity recorded | Project record | Confirm author capacity record | DTL | DTL; IM |  | Next task in this category | DM.06.007
PDM-X0605 | DM_06_008 | Issue team briefing pack | PDM | DM_06 | ST2 | One pack per TTM. | 1 | Y | NONE | N | N | Y | Task Team Coordination work is open | Task Team Coordination predecessor complete | Issue team briefing pack recorded | Project record | Issue team briefing pack record | DTL | DTL; IM |  | Next task in this category | DM.06.008
PDM-X0606 | DM_06_009 | Collect team constraints | PDM | DM_06 | ST2 | Holidays, tools, CDE access. | 1 | Y | NONE | N | N | Y | Task Team Coordination work is open | Task Team Coordination predecessor complete | Collect team constraints recorded | Project record | Collect team constraints record | DTL | DTL; IM |  | Next task in this category | DM.06.009
PDM-X0701 | DM_07_009 | Run coordination workshop | PDM | DM_07 | ST3 | Workshop on interfaces. | 1 | Y | NONE | N | N | Y | Design Coordination work is open | Design Coordination predecessor complete | Run coordination workshop recorded | Project record | Run coordination workshop record | DTL | DTL; IM |  | Next task in this category | DM.07.009
PDM-X0702 | DM_07_010 | Log spatial clashes | PDM | DM_07 | ST3 | Clash to package owners. | 1 | Y | NONE | N | N | Y | Design Coordination work is open | Design Coordination predecessor complete | Log spatial clashes recorded | Project record | Log spatial clashes record | DTL | DTL; IM |  | Next task in this category | DM.07.010
PDM-X0703 | DM_07_011 | Log information clashes | PDM | DM_07 | ST3 | Missing IR between teams. | 1 | Y | NONE | N | N | Y | Design Coordination work is open | Design Coordination predecessor complete | Log information clashes recorded | Project record | Log information clashes record | DTL | DTL; IM |  | Next task in this category | DM.07.011
PDM-X0704 | DM_07_012 | Agree shaft / entry ownership | PDM | DM_07 | ST3 | Shared fabric ownership. | 1 | Y | NONE | N | N | Y | Design Coordination work is open | Design Coordination predecessor complete | Agree shaft / entry ownership recorded | Project record | Agree shaft / entry ownership record | DTL | DTL; IM |  | Next task in this category | DM.07.012
PDM-X0705 | DM_07_013 | Agree service zone rules | PDM | DM_07 | ST3 | WS3 coordination rule. | 1 | Y | NONE | N | N | Y | Design Coordination work is open | Design Coordination predecessor complete | Agree service zone rules recorded | Project record | Agree service zone rules record | DTL | DTL; IM |  | Next task in this category | DM.07.013
PDM-X0706 | DM_07_014 | Agree model federation schedule | PDM | DM_07 | ST3 | When models federate. | 1 | Y | NONE | N | N | Y | Design Coordination work is open | Design Coordination predecessor complete | Agree model federation schedule recorded | Project record | Agree model federation schedule record | DTL | DTL; IM |  | Next task in this category | DM.07.014
PDM-X0707 | DM_07_015 | Agree drawing freeze dates | PDM | DM_07 | ST3 | Freeze before issue. | 1 | Y | NONE | N | N | Y | Design Coordination work is open | Design Coordination predecessor complete | Agree drawing freeze dates recorded | Project record | Agree drawing freeze dates record | DTL | DTL; IM |  | Next task in this category | DM.07.015
PDM-X0801 | DM_08_018 | Measure package % complete | PDM | DM_08 | ST3 | Against earned-progress rule. | 1 | Y | NONE | N | N | Y | Production Oversight work is open | Production Oversight predecessor complete | Measure package % complete recorded | Project record | Measure package % complete record | DTL | DTL; IM |  | Next task in this category | DM.08.018
PDM-X0802 | DM_08_019 | Forecast package finish | PDM | DM_08 | ST3 | Forecast event. | 1 | Y | NONE | N | N | Y | Production Oversight work is open | Production Oversight predecessor complete | Forecast package finish recorded | Project record | Forecast package finish record | DTL | DTL; IM |  | Next task in this category | DM.08.019
PDM-X0803 | DM_08_020 | Flag late packages | PDM | DM_08 | ST3 | Late vs window. | 1 | Y | NONE | N | N | Y | Production Oversight work is open | Production Oversight predecessor complete | Flag late packages recorded | Project record | Flag late packages record | DTL | DTL; IM |  | Next task in this category | DM.08.020
PDM-X0804 | DM_08_021 | Flag blocked packages | PDM | DM_08 | ST3 | Waiting on predecessor. | 1 | Y | NONE | N | N | Y | Production Oversight work is open | Production Oversight predecessor complete | Flag blocked packages recorded | Project record | Flag blocked packages record | DTL | DTL; IM |  | Next task in this category | DM.08.021
PDM-X0805 | DM_08_022 | Update production dashboard | PDM | DM_08 | ST3 | PDM dashboard refresh. | 1 | Y | NONE | N | N | Y | Production Oversight work is open | Production Oversight predecessor complete | Update production dashboard recorded | Project record | Update production dashboard record | DTL | DTL; IM |  | Next task in this category | DM.08.022
PDM-X0806 | DM_08_023 | Brief DTL on production health | PDM | DM_08 | ST3 | Oversight input to DTL-201. | 1 | Y | NONE | N | N | Y | Production Oversight work is open | Production Oversight predecessor complete | Brief DTL on production health recorded | Project record | Brief DTL on production health record | DTL | DTL; IM |  | Next task in this category | DM.08.023
PDM-X0901 | DM_09_010 | Review model maturity vs LOIN | PDM | DM_09 | ST3 | LOD/LOI vs stage. | 1 | Y | NONE | N | N | Y | Reviews work is open | Reviews predecessor complete | Review model maturity vs LOIN recorded | Project record | Review model maturity vs LOIN record | DTL | DTL; IM |  | Next task in this category | DM.09.010
PDM-X0902 | DM_09_011 | Review schedule completeness | PDM | DM_09 | ST3 | Door schedules not before WS4, etc. | 1 | Y | NONE | N | N | Y | Reviews work is open | Reviews predecessor complete | Review schedule completeness recorded | Project record | Review schedule completeness record | DTL | DTL; IM |  | Next task in this category | DM.09.011
PDM-X0903 | DM_09_012 | Review calculation pack | PDM | DM_09 | ST3 | Engineering evidence. | 1 | Y | NONE | N | N | Y | Reviews work is open | Reviews predecessor complete | Review calculation pack recorded | Project record | Review calculation pack record | DTL | DTL; IM |  | Next task in this category | DM.09.012
PDM-X0904 | DM_09_013 | Review specification alignment | PDM | DM_09 | ST3 | Spec vs model. | 1 | Y | NONE | N | N | Y | Reviews work is open | Reviews predecessor complete | Review specification alignment recorded | Project record | Review specification alignment record | DTL | DTL; IM |  | Next task in this category | DM.09.013
PDM-X0905 | DM_09_014 | Review builders-work completeness | PDM | DM_09 | ST3 | Openings and loads. | 1 | Y | NONE | N | N | Y | Reviews work is open | Reviews predecessor complete | Review builders-work completeness recorded | Project record | Review builders-work completeness record | DTL | DTL; IM |  | Next task in this category | DM.09.014
PDM-X1001 | DM_10_011 | Compile gate evidence index | PDM | DM_10 | ST4 | Index for DTL-401. | 1 | Y | NONE | Y | Y | Y | Approvals work is open | Approvals predecessor complete | Compile gate evidence index recorded | Project record | Compile gate evidence index record | DTL | DTL; IM |  | Next task in this category | DM.10.011
PDM-X1002 | DM_07_016 | Confirm no open critical clashes | PDM | DM_07 | ST4 | Gate hygiene. | 1 | Y | NONE | N | N | Y | Approvals work is open | Approvals predecessor complete | Confirm no open critical clashes recorded | Project record | Confirm no open critical clashes record | DTL | DTL; IM |  | Next task in this category | DM.07.016
PDM-X1003 | DM_10_012 | Confirm no open mandatory IR gaps | PDM | DM_10 | ST4 | Gate hygiene. | 1 | Y | NONE | N | N | Y | Approvals work is open | Approvals predecessor complete | Confirm no open mandatory IR gaps recorded | Project record | Confirm no open mandatory IR gaps record | DTL | DTL; IM |  | Next task in this category | DM.10.012
PDM-X1004 | DM_10_013 | Record residual risks at gate | PDM | DM_10 | ST4 | Risks accepted into next stage. | 1 | Y | NONE | Y | Y | Y | Approvals work is open | Approvals predecessor complete | Record residual risks at gate recorded | Project record | Record residual risks at gate record | DTL | DTL; IM |  | Next task in this category | DM.10.013
PDM-X1101 | DM_08_024 | Compile client issue set | PDM | DM_08 | ST5 | Set for DTL-501. | 1 | Y | NONE | N | N | Y | Release Management work is open | Release Management predecessor complete | Compile client issue set recorded | Project record | Compile client issue set record | DTL | DTL; IM |  | Next task in this category | DM.08.024
PDM-X1102 | DM_08_025 | Compile construction issue set | PDM | DM_08 | ST5 | Set for DTL-502. | 1 | Y | NONE | N | N | Y | Release Management work is open | Release Management predecessor complete | Compile construction issue set recorded | Project record | Compile construction issue set record | DTL | DTL; IM |  | Next task in this category | DM.08.025
PDM-X1103 | DM_08_026 | Confirm revision codes | PDM | DM_08 | ST5 | C-issue revision. | 1 | Y | NONE | N | N | Y | Release Management work is open | Release Management predecessor complete | Confirm revision codes recorded | Project record | Confirm revision codes record | DTL | DTL; IM |  | Next task in this category | DM.08.026
PDM-X1104 | DM_08_027 | Confirm transmittal list | PDM | DM_08 | ST5 | What IM will publish. | 1 | Y | NONE | N | N | Y | Release Management work is open | Release Management predecessor complete | Confirm transmittal list recorded | Project record | Confirm transmittal list record | DTL | DTL; IM |  | Next task in this category | DM.08.027
PDM-X1201 | DM_08_028 | Triage RFI by package | PDM | DM_08 | ST6 | RFI to owner package. | 1 | Y | NONE | N | N | Y | Construction Support work is open | Construction Support predecessor complete | Triage RFI by package recorded | Project record | Triage RFI by package record | DTL | DTL; IM |  | Next task in this category | DM.08.028
PDM-X1202 | DM_08_029 | Agree site instruction vs revision | PDM | DM_08 | ST6 | Which path. | 1 | Y | NONE | N | N | Y | Construction Support work is open | Construction Support predecessor complete | Agree site instruction vs revision recorded | Project record | Agree site instruction vs revision record | DTL | DTL; IM |  | Next task in this category | DM.08.029
PDM-X1203 | DM_08_030 | Track revision lag | PDM | DM_08 | ST6 | Days from decision to IM-601. | 1 | Y | NONE | N | N | Y | Construction Support work is open | Construction Support predecessor complete | Track revision lag recorded | Project record | Track revision lag record | DTL | DTL; IM |  | Next task in this category | DM.08.030
PDM-X1204 | DM_08_031 | Protect issued baseline | PDM | DM_08 | ST6 | Do not silently rewrite issued set. | 1 | Y | NONE | N | N | Y | Construction Support work is open | Construction Support predecessor complete | Protect issued baseline recorded | Project record | Protect issued baseline record | DTL | DTL; IM |  | Next task in this category | DM.08.031
PDM-X1301 | DM_08_032 | Confirm package AS-BUILT status | PDM | DM_08 | ST7 | Lifecycle. | 1 | Y | NONE | N | N | Y | Handover work is open | Handover predecessor complete | Confirm package AS-BUILT status recorded | Project record | Confirm package AS-BUILT status record | DTL | DTL; IM |  | Next task in this category | DM.08.032
PDM-X1302 | DM_08_033 | Confirm O&M per package | PDM | DM_08 | ST7 | Handover contents. | 1 | Y | NONE | N | N | Y | Handover work is open | Handover predecessor complete | Confirm O&M per package recorded | Project record | Confirm O&M per package record | DTL | DTL; IM |  | Next task in this category | DM.08.033
PDM-X1303 | DM_08_034 | Confirm commissioning info per package | PDM | DM_08 | ST7 | Handover contents. | 1 | Y | NONE | N | N | Y | Handover work is open | Handover predecessor complete | Confirm commissioning info per package recorded | Project record | Confirm commissioning info per package record | DTL | DTL; IM |  | Next task in this category | DM.08.034
PDM-X1304 | DM_08_035 | Sign design-complete certificate | PDM | DM_08 | ST7 | Input to DTL-704. | 1 | Y | NONE | N | N | Y | Handover work is open | Handover predecessor complete | Sign design-complete certificate recorded | Project record | Sign design-complete certificate record | DTL | DTL; IM |  | Next task in this category | DM.08.035
IM-000 | IM_01_001 | Prepare information environment | IM | IM_01 | ST0 | Ready CDE/project before DTL-015. | 1 | Y | NONE | N | N | Y | DTL-010 appointment | Access | IM ready | Appointment | Readiness |  | DTL | DTL-010 | IM-001 | IM.01.001
IM-001 | IM_01_002 | Configure project | IM | IM_01 | ST0 | Create the project information environment after mobilisation approval. | 2 | Y | NONE | N | N | Y | DTL-015 | Mobilisation approved | Project record live | PEP; Codes | Configured project |  | PDM; DM | DTL-015;PDM-003 | IM-002 | IM.01.002
IM-002 | IM_01_003 | Setup functional breakdown | IM | IM_01 | ST0 | Configure FBs for the project. | 2 | Y | NONE | N | N | Y | Project configured | FB list | FB live | Scope | FB |  | PDM | IM-001 | IM-003 | IM.01.003
IM-003 | IM_01_004 | Setup spatial breakdown | IM | IM_01 | ST0 | Configure spatial per FB (not one list for the project). | 2 | Y | NONE | N | N | Y | FBs live | Levels | Spatial per FB | Levels | fbSpatial |  | PDM | IM-002 | IM-004 | IM.01.004
IM-004 | IM_01_005 | Setup task teams | IM | IM_01 | ST0 | Activate task teams / roles. | 2 | Y | NONE | N | N | Y | Spatials set | Role catalogue | Teams live | Roles | Teams |  | PDM; DTL | IM-003 | IM-005 | IM.01.005
IM-005 | IM_01_006 | Configure information standards | IM | IM_01 | ST0 | Naming, numbering, metadata, classification. | 3 | Y | NONE | N | N | Y | Teams live | Standards pack | Standards live | Standards | Standards |  | DM | IM-004 | IM-006 | IM.01.006
IM-006 | IM_01_007 | Configure templates | IM | IM_01 | ST0 | Information templates bound to AIR. | 2 | Y | NONE | N | N | Y | Standards live | Templates | Templates live | ITE | Templates |  | TTIM | IM-005 | IM-007 | IM.01.007
IM-007 | IM_01_008 | Configure workflows | IM | IM_01 | ST0 | WIP / Shared / Published / gates. | 2 | Y | NONE | N | N | Y | Templates live | Workflow spec | Workflows live | States | Workflows |  | PDM; DM | IM-006 | IM-101 | IM.01.008
IM-101 | IM_03_001 | Create MIDP | IM | IM_03 | ST1 | Create MIDP from packages and stages. FS after PDM-101. | 4 | Y | PLAN | N | N | Y | Scope Package Register | Packages | MIDP draft | PDM-101 | MIDP draft |  | PDM; TTM | PDM-101 | IM-102 | IM.03.001
IM-102 | IM_04_001 | Create TIDPs | IM | IM_04 | ST1 | Create task-team plans from MIDP. | 3 | Y | NONE | N | N | Y | MIDP draft | MIDP | TIDPs | MIDP | TIDPs |  | TTM; TTIM | IM-101 | IM-103 | IM.04.001
IM-103 | IM_07_001 | Configure workflows against MIDP | IM | IM_07 | ST1 | SS with MIDP development. | 2 | Y | NONE | N | N | Y | MIDP in development | MIDP | Workflows aligned | MIDP | Aligned workflows |  | DM | IM-101 | IM-104 | IM.07.001
IM-104 | IM_03_002 | MIDP approval (IM complete) | IM | IM_03 | ST1 | Declare MIDP complete for DTL/PDM approval path. | 1 | Y | NONE | N | Y | Y | MIDP complete | MIDP | MIDP complete record | MIDP | MIDP complete | DTL | PDM; DTL | IM-101;IM-102 | PDM-104 / DTL-105 | IM.03.002
IM-105 | IM_02_001 | Configure information requirements | IM | IM_02 | ST1 | Bind IR / AIR to packages. | 3 | Y | NONE | N | N | Y | Packages exist | AIR | IR bound | AIR; Packages | Bound IR |  | PDM | PDM-101 | IM-106 | IM.02.001
IM-106 | IM_02_002 | Configure information templates on packages | IM | IM_02 | ST1 | Bind templates to packages. | 2 | Y | NONE | N | N | Y | IR bound | Templates | Templates on packages | ITE | Bound templates |  | TTIM | IM-105 | IM-107 | IM.02.002
IM-107 | IM_02_003 | Configure scope packages in the CDE | IM | IM_02 | ST1 | Containers for each package. | 2 | Y | MONITOR | N | N | Y | Templates bound | CDE | Package containers | Packages | Containers |  | DM; PDM | IM-106 | IM-108 | IM.02.003
IM-108 | IM_05_001 | Manage classification | IM | IM_05 | ST1 | Uniclass / project classification live. | 2 | Y | NONE | N | N | Y | Standards live | Tables | Classification live | Uniclass | Classification |  | TTIM | IM-005 | IM-109 | IM.05.001
IM-109 | IM_05_002 | Manage naming conventions | IM | IM_05 | ST1 | Apply naming to containers. | 1 | Y | NONE | N | N | Y | Classification live | Convention | Naming live | Convention | Naming |  | DM | IM-108 | IM-110 | IM.05.002
IM-110 | IM_05_003 | Manage numbering | IM | IM_05 | ST1 | Document / model numbering bands. | 1 | Y | NONE | N | N | Y | Naming live | Series | Numbering live | Series | Numbering |  | DM | IM-109 | IM-111 | IM.05.003
IM-111 | IM_05_004 | Manage metadata | IM | IM_05 | ST1 | Required metadata set. | 2 | Y | NONE | N | N | Y | Numbering live | Schema | Metadata live | Schema | Metadata schema |  | TTIM | IM-110 | IM-201 | IM.05.004
IM-201 | IM_06_001 | Monitor information production | IM | IM_06 | ST2 | SS with package production. | 1 | Y | MONITOR | N | N | Y | PDM-104 | Production feed | Production watch | TIDP | Watch |  | TTM; TTIM | PDM-104 | IM-202 | IM.06.001
IM-202 | IM_06_002 | Monitor compliance | IM | IM_06 | ST2 | SS with production. | 1 | Y | MONITOR | N | N | Y | Production | Rules | Compliance view | IDS; IR | Compliance view |  | TTIM; PDM | IM-201 | IM-203 | IM.06.002
IM-203 | IM_06_003 | Monitor deliverables | IM | IM_06 | ST2 | Watch deliverable creation. | 1 | Y | MONITOR | N | N | Y | Production | Register | Deliverable watch | Register | Watch |  | TTM | IM-201 | IM-204 | IM.06.003
IM-204 | IM_06_004 | Monitor information completeness | IM | IM_06 | ST2 | Completeness vs LOIN / stage. | 1 | Y | MONITOR | N | N | Y | Deliverables moving | LOIN | Completeness view | LOIN | Completeness |  | PDM | IM-203 | IM-205 | IM.06.004
IM-205 | IM_06_005 | Monitor workflows | IM | IM_06 | ST2 | State changes. | 1 | Y | MONITOR | N | N | Y | Workflows live | States | Workflow watch | CDE states | Watch |  | DM | IM-007 | IM-301 | IM.06.005
IM-301 | IM_08_001 | Review metadata | IM | IM_08 | ST3 | FS after peer review complete. | 1 | Y | NONE | N | N | Y | PKG-PEER | Containers | Metadata reviewed | Peer complete | Metadata review |  | TTIM | PKG-PEER | IM-302 | IM.08.001
IM-302 | IM_08_002 | Validate information | IM | IM_08 | ST3 | FS after TTIM review. | 1 | Y | NONE | N | N | Y | PKG-TTIM | Containers | Information validated | TTIM | Validation |  | TTIM; PDM | PKG-TTIM | IM-303 | IM.08.002
IM-303 | IM_08_003 | Validate readiness / compliance confirmation | IM | IM_08 | ST4 | For DTL gate. | 2 | Y | NONE | N | Y | Y | PDM-302 | Approvals | IM compliance confirmation | Approvals | Compliance confirmation |  | PDM; DTL | PDM-302 | DTL-401 | IM.08.003
IM-304 | IM_08_004 | Review classification on containers | IM | IM_08 | ST3 | Classification still correct. | 1 | Y | NONE | N | N | Y | Containers submitted | Class | Class review | Class | Review |  | TTIM | IM-108 | IM-302 | IM.08.004
IM-305 | IM_08_005 | Review information quality | IM | IM_08 | ST3 | Quality sample. | 1 | Y | NONE | N | N | Y | Submitted | Sample | Quality review | Sample | Review |  | TTM | IM-203 | IM-302 | IM.08.005
IM-306 | IM_07_002 | Route approvals | IM | IM_07 | ST3 | Move containers through approval states. | 1 | Y | NONE | N | N | Y | Items waiting | Queue | Routed | Queue | Routed | PDM | PDM; TTM | IM-205 | IM-307 | IM.07.002
IM-307 | IM_07_003 | Manage information state changes | IM | IM_07 | ST3 | WIP / Shared / Published. | 1 | Y | NONE | N | N | Y | Decision made | State | State changed | Decision | State |  | DM | IM-306 | IM-401 | IM.07.003
IM-308 | IM_07_004 | Manage escalations (information) | IM | IM_07 | ST3 | Overdue or blocked containers. | 1 | Y | NONE | N | N | Y | Overdue | Item | Escalation | Item | Escalation | DTL | PDM; DTL |  | DTL-301 | IM.07.004
IM-401 | IM_09_001 | Publish information | IM | IM_09 | ST5 | FS after PDM-302. No publish before PDM approval. | 1 | Y | PUBLISH | Y | N | Y | PDM-302 | Approved containers | Published | Approvals | Published set |  | PDM; DM | PDM-302;DTL-501 | IM-402 | IM.09.001
IM-402 | IM_09_002 | Update registers | IM | IM_09 | ST5 | FS after publish. | 1 | Y | NONE | N | N | Y | Published | Registers | Registers updated | Published | Registers |  | DM | IM-401 | IM-403 | IM.09.002
IM-403 | IM_09_003 | Issue information containers | IM | IM_09 | ST5 | Transmit / issue event. | 1 | Y | PUBLISH | Y | N | Y | Registers updated | Issue list | Containers issued | List | Issue event |  | PDM; DM | IM-402;DTL-502 | IM-601 | IM.09.003
IM-404 | IM_09_004 | Manage shared information | IM | IM_09 | ST5 | Shared state control. | 1 | Y | NONE | N | N | Y | Ready to share | Shared set | Shared managed | Set | Shared |  | DM | IM-307 | IM-401 | IM.09.004
IM-601 | IM_12_001 | Manage revisions | IM | IM_12 | ST6 | Control revised packages on site. | 1 | Y | MONITOR | N | N | Y | Revision approved | Rev | Revision issued | PDM-604 | Revision issue |  | PDM; DM | PDM-604 | IM-602 | IM.12.001
IM-602 | IM_12_002 | Manage updated packages | IM | IM_12 | ST6 | Keep package status REVISED. | 1 | Y | NONE | N | N | Y | Revision issued | Package | Status updated | Package | REVISED |  | PDM | IM-601 | IM-603 | IM.12.002
IM-603 | IM_09_005 | Manage construction information exchanges | IM | IM_09 | ST6 | Exchanges during install. | 1 | Y | NONE | N | N | Y | On site | Exchange | Exchange recorded | Exchange | Record |  | CM; PDM | IM-403 | IM-701 | IM.09.005
IM-701 | IM_11_001 | Review AIM | IM | IM_11 | ST7 | Review AIM present vs required. | 3 | Y | MONITOR | N | N | Y | S6 stable | AIM | AIM review | AIM engine | AIM review |  | PDM; FM | PDM-702 | IM-702 | IM.11.001
IM-702 | IM_10_001 | Review AIR compliance | IM | IM_10 | ST7 | AIR vs AIM. | 2 | Y | NONE | N | N | Y | AIM reviewed | AIR | AIR compliance | AIR | AIR compliance |  | PDM | IM-701 | IM-703 / DTL-702 | IM.10.001
IM-703 | IM_11_002 | Prepare handover and archive packages | IM | IM_11 | ST7 | Build handover + archive sets. | 3 | Y | CLOSE | N | N | Y | AIR compliance | Sets | Handover + archive packs | Registers | Packs |  | DM; PDM | IM-702 | IM-704 | IM.11.002
IM-704 | IM_12_003 | Archive information | IM | IM_12 | ST7 | Store the archive. | 2 | Y | CLOSE | N | N | Y | DTL-708 | Archive pack | Archived | Pack | Archive |  | DM | DTL-708 | IM-705 | IM.12.003
IM-705 | IM_12_004 | Lock information records | IM | IM_12 | ST7 | Prevent further mutation. | 1 | Y | NONE | N | N | Y | Archived | Records | Locked | Archive | Lock |  | DM | IM-704 | IM-706 | IM.12.004
IM-706 | IM_11_003 | Generate final registers | IM | IM_11 | ST7 | Final MIDP/TIDP/issue registers. | 2 | Y | NONE | N | N | Y | Locked | Registers | Final registers | Registers | Final registers |  | PDM | IM-705 | IM-707 | IM.11.003
IM-707 | IM_11_004 | Support lessons learned | IM | IM_11 | ST7 | Provide information evidence to DTL-705. | 1 | Y | NONE | N | N | Y | Final registers | Evidence | Evidence pack | Logs | Evidence |  | DTL | IM-706 | — | IM.11.004
IM-X0101 | IM_12_005 | Confirm CDE project code | IM | IM_12 | ST0 | Code stable before naming. | 1 | Y | NONE | N | N | Y | Project Setup work is open | Project Setup predecessor complete | Confirm CDE project code recorded | Project record | Confirm CDE project code record | DTL | PDM |  | Next task in this category | IM.12.005
IM-X0102 | IM_12_006 | Confirm originator codes | IM | IM_12 | ST0 | ISO naming originators. | 1 | Y | NONE | N | N | Y | Project Setup work is open | Project Setup predecessor complete | Confirm originator codes recorded | Project record | Confirm originator codes record | DTL | PDM |  | Next task in this category | IM.12.006
IM-X0103 | IM_12_007 | Confirm status / revision scheme | IM | IM_12 | ST0 | WIP Shared Published. | 1 | Y | NONE | N | N | Y | Project Setup work is open | Project Setup predecessor complete | Confirm status / revision scheme recorded | Project record | Confirm status / revision scheme record | DTL | PDM |  | Next task in this category | IM.12.007
IM-X0104 | IM_12_008 | Confirm volume / system codes | IM | IM_12 | ST0 | Naming tokens. | 1 | Y | NONE | N | N | Y | Project Setup work is open | Project Setup predecessor complete | Confirm volume / system codes recorded | Project record | Confirm volume / system codes record | DTL | PDM |  | Next task in this category | IM.12.008
IM-X0301 | IM_12_009 | Map packages to MIDP rows | IM | IM_12 | ST1 | One package family per row set. | 1 | Y | NONE | N | N | Y | MIDP work is open | MIDP predecessor complete | Map packages to MIDP rows recorded | Project record | Map packages to MIDP rows record | DTL | PDM |  | Next task in this category | IM.12.009
IM-X0302 | IM_12_010 | Map stages to MIDP columns | IM | IM_12 | ST1 | Stage applicability. | 1 | Y | NONE | N | N | Y | MIDP work is open | MIDP predecessor complete | Map stages to MIDP columns recorded | Project record | Map stages to MIDP columns record | DTL | PDM |  | Next task in this category | IM.12.010
IM-X0303 | IM_12_011 | Map roles to MIDP responsibility | IM | IM_12 | ST1 | RACI on rows. | 1 | Y | NONE | N | N | Y | MIDP work is open | MIDP predecessor complete | Map roles to MIDP responsibility recorded | Project record | Map roles to MIDP responsibility record | DTL | PDM |  | Next task in this category | IM.12.011
IM-X0304 | IM_12_012 | Issue MIDP revision after package change | IM | IM_12 | ST1 | Keep MIDP honest. | 1 | Y | NONE | N | N | Y | MIDP work is open | MIDP predecessor complete | Issue MIDP revision after package change recorded | Project record | Issue MIDP revision after package change record | DTL | PDM |  | Next task in this category | IM.12.012
IM-X0305 | IM_12_013 | Compare generated vs imported MIDP | IM | IM_12 | ST1 | FORMA / import check. | 1 | Y | NONE | N | N | Y | MIDP work is open | MIDP predecessor complete | Compare generated vs imported MIDP recorded | Project record | Compare generated vs imported MIDP record | DTL | PDM |  | Next task in this category | IM.12.013
IM-X0401 | IM_12_014 | Seed TIDP from packages | IM | IM_12 | ST1 | Model/coord/verify/review/approve. | 1 | Y | NONE | N | N | Y | TIDP work is open | TIDP predecessor complete | Seed TIDP from packages recorded | Project record | Seed TIDP from packages record | DTL | PDM |  | Next task in this category | IM.12.014
IM-X0402 | IM_12_015 | Rebuild TIDP after package owner move | IM | IM_12 | ST1 | Drag-drop rule. | 1 | Y | NONE | N | N | Y | TIDP work is open | TIDP predecessor complete | Rebuild TIDP after package owner move recorded | Project record | Rebuild TIDP after package owner move record | DTL | PDM |  | Next task in this category | IM.12.015
IM-X0403 | IM_12_016 | Confirm TIDP authors named | IM | IM_12 | ST1 | IA on activities. | 1 | Y | NONE | N | N | Y | TIDP work is open | TIDP predecessor complete | Confirm TIDP authors named recorded | Project record | Confirm TIDP authors named record | DTL | PDM |  | Next task in this category | IM.12.016
IM-X0404 | IM_12_017 | Confirm TIDP verify is not skipped | IM | IM_12 | ST1 | Hard rule. | 1 | Y | NONE | N | N | Y | TIDP work is open | TIDP predecessor complete | Confirm TIDP verify is not skipped recorded | Project record | Confirm TIDP verify is not skipped record | DTL | PDM |  | Next task in this category | IM.12.017
IM-X0501 | IM_12_018 | Lock classification tables | IM | IM_12 | ST1 | Who may edit Uniclass maps. | 1 | Y | NONE | N | N | Y | Information Governance work is open | Information Governance predecessor complete | Lock classification tables recorded | Project record | Lock classification tables record | DTL | PDM |  | Next task in this category | IM.12.018
IM-X0502 | IM_12_019 | Lock template library | IM | IM_12 | ST1 | Who may edit templates. | 1 | Y | NONE | N | N | Y | Information Governance work is open | Information Governance predecessor complete | Lock template library recorded | Project record | Lock template library record | DTL | PDM |  | Next task in this category | IM.12.019
IM-X0503 | IM_12_020 | Record standard deviations | IM | IM_12 | ST1 | Project deviations log. | 1 | Y | NONE | N | N | Y | Information Governance work is open | Information Governance predecessor complete | Record standard deviations recorded | Project record | Record standard deviations record | DTL | PDM |  | Next task in this category | IM.12.020
IM-X0504 | IM_12_021 | Audit catalogue changes | IM | IM_12 | ST1 | Governance audit. | 1 | Y | NONE | N | N | Y | Information Governance work is open | Information Governance predecessor complete | Audit catalogue changes recorded | Project record | Audit catalogue changes record | DTL | PDM |  | Next task in this category | IM.12.021
IM-X0601 | IM_12_022 | Watch container count vs plan | IM | IM_12 | ST2 | Production metric. | 1 | Y | NONE | N | N | Y | Information Production work is open | Information Production predecessor complete | Watch container count vs plan recorded | Project record | Watch container count vs plan record | DTL | PDM |  | Next task in this category | IM.12.022
IM-X0602 | IM_12_023 | Watch stale WIP | IM | IM_12 | ST2 | WIP older than policy. | 1 | Y | NONE | N | N | Y | Information Production work is open | Information Production predecessor complete | Watch stale WIP recorded | Project record | Watch stale WIP record | DTL | PDM |  | Next task in this category | IM.12.023
IM-X0603 | IM_12_024 | Watch missing metadata on new containers | IM | IM_12 | ST2 | Quality. | 1 | Y | NONE | N | N | Y | Information Production work is open | Information Production predecessor complete | Watch missing metadata on new containers recorded | Project record | Watch missing metadata on new containers record | DTL | PDM |  | Next task in this category | IM.12.024
IM-X0801 | IM_12_025 | Validate LOI parameters for stage | IM | IM_12 | ST3 | ATA_ set for stage. | 1 | Y | NONE | N | N | Y | Information Validation work is open | Information Validation predecessor complete | Validate LOI parameters for stage recorded | Project record | Validate LOI parameters for stage record | DTL | PDM |  | Next task in this category | IM.12.025
IM-X0802 | IM_12_026 | Validate IDS fail rows | IM | IM_12 | ST3 | IDS engine. | 1 | Y | NONE | N | N | Y | Information Validation work is open | Information Validation predecessor complete | Validate IDS fail rows recorded | Project record | Validate IDS fail rows record | DTL | PDM |  | Next task in this category | IM.12.026
IM-X0803 | IM_12_027 | Validate classification codes on elements | IM | IM_12 | ST3 | Class. | 1 | Y | NONE | N | N | Y | Information Validation work is open | Information Validation predecessor complete | Validate classification codes on elements recorded | Project record | Validate classification codes on elements record | DTL | PDM |  | Next task in this category | IM.12.027
IM-X0901 | IM_12_028 | Record exchange event | IM | IM_12 | ST5 | Not a CDE state. | 1 | Y | NONE | N | N | Y | Information Exchange work is open | Information Exchange predecessor complete | Record exchange event recorded | Project record | Record exchange event record | DTL | PDM |  | Next task in this category | IM.12.028
IM-X0902 | IM_12_029 | Confirm shared vs published | IM | IM_12 | ST5 | State honesty. | 1 | Y | PUBLISH | Y | N | Y | Information Exchange work is open | Information Exchange predecessor complete | Confirm shared vs published recorded | Project record | Confirm shared vs published record | DTL | PDM |  | Next task in this category | IM.12.029
IM-X0903 | IM_12_030 | Issue transmittal | IM | IM_12 | ST5 | With IM-403. | 1 | Y | NONE | N | N | Y | Information Exchange work is open | Information Exchange predecessor complete | Issue transmittal recorded | Project record | Issue transmittal record | DTL | PDM |  | Next task in this category | IM.12.030
IM-X1001 | IM_10_002 | Report discipline compliance | IM | IM_10 | ST3 | Why HVAC is low. | 1 | Y | NONE | N | N | Y | Compliance work is open | Compliance predecessor complete | Report discipline compliance recorded | Project record | Report discipline compliance record | DTL | PDM |  | Next task in this category | IM.10.002
IM-X1002 | IM_12_031 | Report AIR gaps | IM | IM_12 | ST3 | AIR agent input. | 1 | Y | NONE | N | N | Y | Compliance work is open | Compliance predecessor complete | Report AIR gaps recorded | Project record | Report AIR gaps record | DTL | PDM |  | Next task in this category | IM.12.031
IM-X1003 | IM_12_032 | Report gate information readiness | IM | IM_12 | ST3 | IM-303 evidence. | 1 | Y | NONE | Y | Y | Y | Compliance work is open | Compliance predecessor complete | Report gate information readiness recorded | Project record | Report gate information readiness record | DTL | PDM |  | Next task in this category | IM.12.032
IM-X1101 | IM_12_033 | Compute AIM present vs required | IM | IM_12 | ST7 | AIM%. | 1 | Y | NONE | N | N | Y | Handover work is open | Handover predecessor complete | Compute AIM present vs required recorded | Project record | Compute AIM present vs required record | DTL | PDM |  | Next task in this category | IM.12.033
IM-X1102 | IM_12_034 | List assets not handover-ready | IM | IM_12 | ST7 | AIM list. | 1 | Y | NONE | N | N | Y | Handover work is open | Handover predecessor complete | List assets not handover-ready recorded | Project record | List assets not handover-ready record | DTL | PDM |  | Next task in this category | IM.12.034
IM-X1103 | IM_12_035 | Prepare COBie / AIM export set | IM | IM_12 | ST7 | If specified. | 1 | Y | NONE | N | N | Y | Handover work is open | Handover predecessor complete | Prepare COBie / AIM export set recorded | Project record | Prepare COBie / AIM export set record | DTL | PDM |  | Next task in this category | IM.12.035
IM-X1201 | IM_12_036 | Confirm lock list | IM | IM_12 | ST7 | What gets locked. | 1 | Y | NONE | N | N | Y | Archive work is open | Archive predecessor complete | Confirm lock list recorded | Project record | Confirm lock list record | DTL | PDM |  | Next task in this category | IM.12.036
IM-X1202 | IM_12_037 | Confirm retention policy | IM | IM_12 | ST7 | How long. | 1 | Y | NONE | N | N | Y | Archive work is open | Archive predecessor complete | Confirm retention policy recorded | Project record | Confirm retention policy record | DTL | PDM |  | Next task in this category | IM.12.037
IM-X1203 | IM_12_038 | Handover archive index to DTL | IM | IM_12 | ST7 | DTL-708 evidence. | 1 | Y | CLOSE | N | N | Y | Archive work is open | Archive predecessor complete | Handover archive index to DTL recorded | Project record | Handover archive index to DTL record | DTL | PDM |  | Next task in this category | IM.12.038

## DEPENDENCIES
DependencyId | PredecessorTaskCode | SuccessorTaskCode | DependencyType | LagDays
DEP-0001 | DTL-000 | DTL-001 | FS | 0
DEP-0002 | DTL-001 | DTL-002 | FS | 0
DEP-0003 | DTL-002 | DTL-003 | FS | 0
DEP-0004 | DTL-003 | DTL-004 | FS | 0
DEP-0005 | DTL-004 | DTL-005 | FS | 0
DEP-0006 | DTL-005 | DTL-006 | FS | 0
DEP-0007 | DTL-006 | DTL-007 | FS | 0
DEP-0008 | DTL-007 | DTL-008 | FS | 0
DEP-0009 | DTL-008 | DTL-009 | FS | 0
DEP-0010 | DTL-009 | DTL-010 | FS | 0
DEP-0011 | DTL-010 | DTL-011 | FS | 0
DEP-0012 | DTL-011 | DTL-012 | FS | 0
DEP-0013 | DTL-012 | DTL-013 | FS | 0
DEP-0014 | DTL-013 | DTL-014 | FS | 1
DEP-0015 | PDM-003 | DTL-014 | FS | 1
DEP-0016 | DTL-014 | DTL-015 | FS | 0
DEP-0017 | IM-001 | DTL-101 | FS | 0
DEP-0018 | PDM-003 | DTL-101 | FS | 0
DEP-0019 | PDM-103 | DTL-102 | FS | 1
DEP-0020 | IM-101 | DTL-102 | FS | 1
DEP-0021 | PDM-102 | DTL-103 | FS | 0
DEP-0022 | PDM-003 | DTL-104 | FS | 0
DEP-0023 | IM-104 | DTL-105 | FS | 0
DEP-0024 | DTL-102 | DTL-106 | FS | 0
DEP-0025 | PDM-201 | DTL-201 | FS | 0
DEP-0026 | DTL-103 | DTL-202 | FS | 0
DEP-0027 | DTL-013 | DTL-203 | FS | 0
DEP-0028 | PDM-202 | DTL-303 | FS | 0
DEP-0029 | PDM-303 | DTL-401 | FS | 0
DEP-0030 | IM-303 | DTL-401 | FS | 0
DEP-0031 | DTL-401 | DTL-402 | FS | 0
DEP-0032 | DTL-401 | DTL-403 | FS | 0
DEP-0033 | DTL-402 | DTL-501 | FS | 0
DEP-0034 | PDM-501 | DTL-501 | FS | 0
DEP-0035 | DTL-501 | DTL-502 | FS | 0
DEP-0036 | PDM-502 | DTL-502 | FS | 0
DEP-0037 | IM-601 | DTL-601 | FS | 0
DEP-0038 | PDM-603 | DTL-603 | FS | 0
DEP-0039 | DTL-103 | DTL-604 | FS | 0
DEP-0040 | PDM-701 | DTL-701 | FS | 0
DEP-0041 | IM-701 | DTL-701 | FS | 0
DEP-0042 | IM-702 | DTL-702 | FS | 0
DEP-0043 | DTL-702 | DTL-703 | FS | 0
DEP-0044 | DTL-703 | DTL-704 | FS | 0
DEP-0045 | DTL-704 | DTL-705 | FS | 0
DEP-0046 | DTL-705 | DTL-706 | FS | 0
DEP-0047 | DTL-706 | DTL-707 | FS | 0
DEP-0048 | IM-703 | DTL-708 | FS | 0
DEP-0049 | DTL-708 | DTL-709 | FS | 0
DEP-0050 | DTL-009 | PDM-000 | FS | 0
DEP-0051 | DTL-015 | PDM-001 | FS | 0
DEP-0052 | PDM-001 | PDM-002 | FS | 0
DEP-0053 | PDM-002 | PDM-003A | FS | 0
DEP-0054 | PDM-003A | PDM-003B | FS | 0
DEP-0055 | PDM-003B | PDM-003C | FS | 0
DEP-0056 | PDM-003C | PDM-003D | FS | 0
DEP-0057 | PDM-003D | PDM-003 | FS | 1
DEP-0058 | PDM-003 | PDM-004 | FS | 0
DEP-0059 | PDM-004 | PDM-005 | FS | 0
DEP-0060 | PDM-003 | PDM-101 | FS | 0
DEP-0061 | PDM-101 | PDM-102 | FS | 0
DEP-0062 | PDM-102 | PDM-103 | FS | 1
DEP-0063 | IM-104 | PDM-104 | FS | 0
DEP-0064 | PDM-103 | PDM-104 | FS | 0
DEP-0065 | DTL-102 | PDM-104 | FS | 0
DEP-0066 | PDM-003 | PDM-105 | FS | 0
DEP-0067 | PDM-105 | PDM-106 | FS | 0
DEP-0068 | PDM-103 | PDM-107 | FS | 0
DEP-0069 | PDM-107 | PDM-108 | FS | 0
DEP-0070 | PDM-102 | PDM-109 | FS | 0
DEP-0071 | PDM-104 | PDM-201 | FS | 0
DEP-0072 | PDM-201 | PDM-202 | FS | 0
DEP-0073 | PDM-104 | PDM-204 | FS | 0
DEP-0074 | PKG-PRODUCE | PDM-205 | FS | 0
DEP-0075 | PKG-TTM | PDM-301 | FS | 0
DEP-0076 | PDM-301 | PDM-302 | FS | 0
DEP-0077 | PDM-302 | PDM-303 | FS | 0
DEP-0078 | PDM-201 | PDM-304 | FS | 0
DEP-0079 | PDM-202 | PDM-305 | FS | 0
DEP-0080 | PDM-101 | PDM-306 | FS | 0
DEP-0081 | PDM-102 | PDM-307 | FS | 0
DEP-0082 | PKG-PRODUCE | PDM-308 | FS | 0
DEP-0083 | IM-202 | PDM-309 | FS | 0
DEP-0084 | IM-202 | PDM-310 | FS | 0
DEP-0085 | DTL-403 | PDM-401 | FS | 0
DEP-0086 | PDM-401 | PDM-402 | FS | 0
DEP-0087 | DTL-402 | PDM-501 | FS | 0
DEP-0088 | PDM-302 | PDM-501 | FS | 0
DEP-0089 | PDM-501 | PDM-502 | FS | 0
DEP-0090 | IM-401 | PDM-503 | FS | 0
DEP-0091 | PDM-601 | PDM-602 | FS | 0
DEP-0092 | PDM-602 | PDM-603 | FS | 0
DEP-0093 | PKG-PRODUCE | PDM-604 | FS | 0
DEP-0094 | PDM-302 | PDM-701 | FS | 0
DEP-0095 | IM-702 | PDM-702 | FS | 0
DEP-0096 | PDM-702 | PDM-703 | FS | 0
DEP-0097 | PDM-701 | PDM-704 | FS | 0
DEP-0098 | PDM-703 | PDM-704 | FS | 0
DEP-0099 | DTL-010 | IM-000 | FS | 0
DEP-0100 | DTL-015 | IM-001 | FS | 0
DEP-0101 | PDM-003 | IM-001 | FS | 0
DEP-0102 | IM-001 | IM-002 | FS | 0
DEP-0103 | IM-002 | IM-003 | FS | 0
DEP-0104 | IM-003 | IM-004 | FS | 0
DEP-0105 | IM-004 | IM-005 | FS | 0
DEP-0106 | IM-005 | IM-006 | FS | 0
DEP-0107 | IM-006 | IM-007 | FS | 0
DEP-0108 | PDM-101 | IM-101 | FS | 1
DEP-0109 | IM-101 | IM-102 | FS | 0
DEP-0110 | IM-101 | IM-103 | FS | 0
DEP-0111 | IM-101 | IM-104 | FS | 0
DEP-0112 | IM-102 | IM-104 | FS | 0
DEP-0113 | PDM-101 | IM-105 | FS | 0
DEP-0114 | IM-105 | IM-106 | FS | 0
DEP-0115 | IM-106 | IM-107 | FS | 0
DEP-0116 | IM-005 | IM-108 | FS | 0
DEP-0117 | IM-108 | IM-109 | FS | 0
DEP-0118 | IM-109 | IM-110 | FS | 0
DEP-0119 | IM-110 | IM-111 | FS | 0
DEP-0120 | PDM-104 | IM-201 | FS | 0
DEP-0121 | IM-201 | IM-202 | FS | 0
DEP-0122 | IM-201 | IM-203 | FS | 0
DEP-0123 | IM-203 | IM-204 | FS | 0
DEP-0124 | IM-007 | IM-205 | FS | 0
DEP-0125 | PKG-PEER | IM-301 | FS | 0
DEP-0126 | PKG-TTIM | IM-302 | FS | 0
DEP-0127 | PDM-302 | IM-303 | FS | 0
DEP-0128 | IM-108 | IM-304 | FS | 0
DEP-0129 | IM-203 | IM-305 | FS | 0
DEP-0130 | IM-205 | IM-306 | FS | 0
DEP-0131 | IM-306 | IM-307 | FS | 0
DEP-0132 | PDM-302 | IM-401 | FS | 0
DEP-0133 | DTL-501 | IM-401 | FS | 0
DEP-0134 | IM-401 | IM-402 | FS | 0
DEP-0135 | IM-402 | IM-403 | FS | 0
DEP-0136 | DTL-502 | IM-403 | FS | 0
DEP-0137 | IM-307 | IM-404 | FS | 0
DEP-0138 | PDM-604 | IM-601 | FS | 0
DEP-0139 | IM-601 | IM-602 | FS | 0
DEP-0140 | IM-403 | IM-603 | FS | 0
DEP-0141 | PDM-702 | IM-701 | FS | 0
DEP-0142 | IM-701 | IM-702 | FS | 0
DEP-0143 | IM-702 | IM-703 | FS | 0
DEP-0144 | DTL-708 | IM-704 | FS | 0
DEP-0145 | IM-704 | IM-705 | FS | 0
DEP-0146 | IM-705 | IM-706 | FS | 0
DEP-0147 | IM-706 | IM-707 | FS | 0

## SCOPE_PACKAGE_LINKS
TaskCode | PackageInteraction | PackageType | RequiredStage | RequiredApproval
PM_05_008 | MONITOR | Ss Production Package | ST2
PM_05_012 | MONITOR | Ss Production Package | ST3
PM_09_001 | MONITOR | Ss Production Package | ST6
PM_11_001 | CLOSE | Ss Production Package | ST7 | Client
PM_11_005 | CLOSE | Ss Production Package | ST7
DM_05_001 | CREATE | Ss Production Package | ST1
DM_05_002 | PLAN | Ss Production Package | ST1 | DTL
DM_04_001 | CREATE | Ss Production Package | ST1 | DTL
DM_08_001 | PLAN | Ss Production Package | ST1 | DTL
DM_07_001 | MONITOR | Ss Production Package | ST2
DM_07_004 | REVIEW | Ss Production Package | ST2
DM_10_001 | REVIEW | Ss Production Package | ST3
DM_10_002 | APPROVE | Ss Production Package | ST3 | DTL
DM_10_007 | APPROVE | Ss Production Package | ST5 | DTL
DM_10_008 | ASSIGN | Ss Production Package | ST5
IM_03_001 | PLAN | Ss Production Package | ST1
IM_02_003 | MONITOR | Ss Production Package | ST1
IM_06_001 | MONITOR | Ss Production Package | ST2
IM_06_002 | MONITOR | Ss Production Package | ST2
IM_06_003 | MONITOR | Ss Production Package | ST2
IM_06_004 | MONITOR | Ss Production Package | ST2
IM_06_005 | MONITOR | Ss Production Package | ST2
IM_09_001 | PUBLISH | Ss Production Package | ST5
IM_09_003 | PUBLISH | Ss Production Package | ST5
IM_12_001 | MONITOR | Ss Production Package | ST6
IM_11_001 | MONITOR | Ss Production Package | ST7
IM_11_002 | CLOSE | Ss Production Package | ST7
IM_12_003 | CLOSE | Ss Production Package | ST7
IM_12_029 | PUBLISH | Ss Production Package | ST5 | DTL
IM_12_038 | CLOSE | Ss Production Package | ST7 | DTL

## ROLES
RoleCode | RoleName | Family
DTL | Delivery Team Lead | Leadership
PDM | Project Delivery Manager | Leadership
IM | Information Manager | Leadership
DM | Document Manager | Information
TTM | Task Team Manager | Task team
TTIM | Task Team Information Manager | Task team
IA | Information Author | Task team
PR | Peer Reviewer | Task team
CON-CM | Construction Manager | Construction
CON-RE | Resident Engineer | Construction

## TASK_CATEGORIES
CategoryCode | CategoryName | RoleFamily
PM_01 | Opportunity | DTL
PM_02 | Initiation | DTL
PM_03 | Mobilisation | DTL
PM_04 | Planning | DTL
PM_05 | Oversight | DTL
PM_06 | Commercial | DTL
PM_07 | Governance | DTL
PM_08 | Stage Gates | DTL
PM_09 | Construction | DTL
PM_10 | Handover | DTL
PM_11 | Closeout | DTL
DM_01 | Requirements | PDM
DM_02 | Mobilisation | PDM
DM_03 | Delivery Strategy | PDM
DM_04 | Production Planning | PDM
DM_05 | Scope Package Planning | PDM
DM_06 | Task Team Coordination | PDM
DM_07 | Design Coordination | PDM
DM_08 | Production Oversight | PDM
DM_09 | Reviews | PDM
DM_10 | Approvals | PDM
DM_11 | Release Management | PDM
DM_12 | Construction Support | PDM
DM_13 | Handover | PDM
IM_01 | Project Setup | IM
IM_02 | Information Planning | IM
IM_03 | MIDP | IM
IM_04 | TIDP | IM
IM_05 | Information Governance | IM
IM_06 | Information Production | IM
IM_07 | Workflow Management | IM
IM_08 | Information Validation | IM
IM_09 | Information Exchange | IM
IM_10 | Compliance | IM
IM_11 | Handover | IM
IM_12 | Archive | IM

## README
Atana Master Role Catalogue v1.0
Pilot import/export. Filter ROLE_TASKS by Role, Category, Stage. Do not flatten codes — TaskCode is the WBS token (PM.04.015 style).
PackageInteraction: NONE ¦ PLAN ¦ CREATE ¦ ASSIGN ¦ REVIEW ¦ APPROVE ¦ PUBLISH ¦ MONITOR ¦ CLOSE