## Cover
ATANA
Operating Model & Governance
RACI · decision rights · escalation · object duties
Version 1.0 · 31 August 2026 · Does not redesign engines · Companion to docs/OPERATING-MODEL.md
How to read the codes
Code | Meaning
R | Responsible — does the work (draft or maintain)
A | Accountable — one owner; loses sleep
C | Consulted — review before approve
I | Informed — consumer
Owner | Accountable for fitness of the object
Custodian | Versions, access, audit completeness
Approver | May change DRAFT → ACTIVE / lock a gate
FRRM | O Originate · A Approve · V Verify · R Review · P Publish — deliverable workflow only
Admin tiers (unchanged): SYSADMIN → ORGADMIN → PROJECTADMIN → TTM. TTM cannot edit global rules.
Precedence (unchanged): USER > ASSET > PROJECT > ORGANISATION > SYSTEM.

## Roles
Role catalogue
Code | Role | Plane | Kind | Primary duty
AP | Appointing party sponsor | Org / Project | Delivery | Owns OIR; accepts PIR/EIR
AO | Asset owner | Org / Ops | Delivery | Owns AIR intent and AIM accept
PDM | Project delivery manager | Project | Delivery | Time, cost, stage decision with IM
IM | Information Manager | Project | Delivery | Custodian of the project information OS
DM | Document / CDE manager | Project | Delivery | Container state in the CDE
DTL | Discipline lead | Project | Delivery | Technical fitness of a discipline package
TTM | Task team manager | Project | Delivery | Team output and TIDP
TTIM | Task team information manager | Project | Delivery | Team IR / IDS hygiene
IA | Information author | Project | Delivery | Creates containers and parameter values
PR | Peer reviewer | Project | Delivery | Reviews before Shared
FM | Facility manager | Ops | Delivery | Consumes AIM; ops observations after handover
OPS | Operations manager | Ops | Delivery | Owns live regime; not AIR
OGB | Organisation Governance Board | Organisation | Steward | Policy, exceptions, steward appointments
PIM | Portfolio information manager | Portfolio | Steward | Reuse, lessons, benchmark readiness
CS | Classification steward | Organisation | Steward | Uniclass and mapping tables
TS | Template steward | Organisation | Steward | Information templates + ATA_ZZ
GS | Graph steward | Organisation | Steward | Node / rel kinds, query catalogue
AIG | AI governance officer | Organisation | Steward | Allowed models, tool scopes, accept rules
TWS | Twin steward | Ops | Steward | DTDL versions, identity to AIM
AS | Asset library steward | Organisation | Steward | Asset types
SS | System library steward | Organisation | Steward | System types
SP | Space library steward | Organisation | Steward | Space types
SYSADMIN | Platform administrator | Platform | Admin | Tenants, runtime, encryption
ORGADMIN | Organisation administrator | Organisation | Admin | Policy, catalogues, role catalogue
PROJECTADMIN | Project administrator | Project | Admin | Bindings, membership, thresholds in band

## Object duties
Owner · Custodian · Approver · Contributor · Reviewer · Consumer
Object | Owner | Custodian | Approver | Contributor | Reviewer | Consumer | Notes
OIR | AP | PIM or IM | AP | IM, PIM, client SME | AO, H&S as named | All appointed parties | Projects inherit; no mid-gate change without exception
PIR | AP | IM | AP | IM, PDM | AO, DTL | Task teams | Cannot weaken OIR
EIR | AP | IM | AP | IM, PDM, DTL | Lead appointed commercial | All appointed parties | Post-award change = variation
AIR | AO | IM then FM | AO | IM, TS, DTL, TTIM | FM, CS | IA, twin, CMMS | Project proposes; AO activates type
AIM | AO | IM then FM | AO at handover; IM snapshot | IA, TTIM | IM, FM | Twin, CMMS, exec | Formula present/required is not negotiable
IDS spec | TS | TS | TS | TS, TTIM | DTL | IM, engines | Spec is a catalogue object
IDS run | IM | IM | IM (authoritative run) | TTIM, IA | DTL | Graph, Decide | Fail is observation until IM uses it as gate input
Scope package | TTM | TTIM | TTM + IM if locked | DTL, IA | IM, PDM | Authors, PDM, Decide | Unlock = IM + TTM
Information template | TS | TS | OGB or delegated TS | IM, DTL, CS | CS, AO if AIR-facing | All projects | Project clone expires unless promoted
Information requirement | Parent (AIR/EIR) | IM | Parent owner | TTIM, TS | DTL | IA, IDS
Deliverable plan row | TTM | TTIM | TTM then IM/PDM | IA | PR, TTIM | Project | Atana SoR
Deliverable file | CDE | DM | IM + PDM (Publish) | IA | PR | Project + archive | CDE SoR for bytes
Workflow catalogue | ORGADMIN | ORGADMIN | OGB | PROJECTADMIN | PDM, DM | All delivery roles | TTM cannot skip Verify
Workflow instance | IM | IM | IM | TTM | PDM, DM | Team
Knowledge graph schema | GS | GS | GS + OGB | GS | AIG | Decide, Copilot | Organisation event
Knowledge graph data | IM | IM | IM | Engines, IM | AIG if agent-wrote | Decide | Project event
AI recommendation | AIG (policy) | IM | Named by class A–F | Agents, Decide | IM; AO if AIM | Assignee | No auto-write AIR/AIM
Asset library | AS | AS | OGB or AS | IM, DTL | CS | All projects
System library | SS | SS | OGB or SS | IM, DTL | CS | All projects
Space library | SP | SP | OGB or SP | IM | CS | All projects
Classification library | CS | CS | OGB | TS, AS, SS, SP | IM community | All engines | Project may propose only

## RACI
RACI — objects × roles (A = one only per row)
Object | AP | AO | PDM | IM | DM | DTL | TTM | TTIM | IA | PR | FM | PIM | CS | TS | GS | AIG | TWS | OGB
OIR | A | C |  | R | [7 empty] | R | [5 empty] | C
PIR | A | C | C | R |  | C
EIR | A |  | C | R |  | C | [11 empty] | I
AIR |  | A |  | R |  | C |  | C | I |  | C |  | C | C
AIM |  | A | I | R |  |  |  | C | R |  | C | [5 empty] | C
IDS spec |  |  |  | C |  | C |  | C | [5 empty] | A |  |  |  | I
IDS run |  |  |  | A |  | C |  | R | R |  |  |  |  | I
Scope package |  |  | C | C |  | C | A | R | R
Template |  | C |  | C |  | C | [6 empty] | C | A |  |  |  | A
IR |  | A |  | R |  | C |  | R | [5 empty] | C
Deliverable plan |  |  | C | C |  |  | A | R | R | C
Deliverable file |  |  | A | A | R |  | C |  | R | C
Workflow catalogue |  |  | C | C | C | [12 empty] | A
Graph schema |  |  |  | I | [10 empty] | A | C |  | A
Graph data |  |  | I | A | [10 empty] | C | C
AI recommendation |  | C | C | A | [11 empty] | C |  | I
Asset library |  |  |  | C |  | C | [6 empty] | C |  |  |  |  | A
System library |  |  |  | C |  | C | [6 empty] | C |  |  |  |  | A
Space library |  |  |  | C | [8 empty] | C |  |  |  |  | A
Classification |  |  |  | C | [8 empty] | A | C |  |  |  | A
Legend
A | Accountable (one per object; Template/libraries may show OGB + steward as joint A for activate)
R | Responsible
C | Consulted
I | Informed

## Decision rights
Decision rights
Decision | Rights holder | Must consult | Escalate if | Forbidden
Publish organisation template | TS + OGB | CS, IM community | AIR impact unknown | Project-only silent fork kept after close
Activate AIR type | AO | IM, FM, TS | Conflicts with EIR | TTM activating org AIR
Change Stage 4 threshold | ORGADMIN if 90–98% | IM, PDM | Below 90% or programme waive → OGB | PDM override of a fail without AP exception
Lock / unlock package | IM + TTM | PDM | Commercial impact | USER_REMOVED on locked package
Accept AIM handover | AO | IM, FM, TWS | Completeness < gate | Agent auto-accept
Accept AI action class B | IM | Affected TTM | AIM/AIR write requested | Auto-assign without IM
Accept AI action class C | IM + PDM | TTM | Changes MIDP after gate | Agent generate-and-publish
Accept AI action class E | TS + OGB | CS, AO | Breaks IDS | Any auto-mutate of template
Accept AI action class F | AO | IM, FM | Missing LOI 4 | Any auto-handover
Add graph node kind | GS + OGB | AIG | Breaks /v1/ask | Project-defined kinds
Bind primary CDE | PROJECTADMIN | IM, DM | Second file SoR requested | Two file SoRs
Promote lessons to catalogue | PIM + steward | OGB | Changes AIR | Copy-paste into live AIR
Skip Verify state | — | — | — | Always forbidden
Write CDE bytes from Atana | IM with naming.enforce | DM | Rename collision | Default Wave 1 write-back

## Escalation & SOP
Escalation
Level | SLA | Path | Typical trigger
L1 | 1 working day | TTIM → IM | Mapping conflict, missing parameter
L2 | 3 working days | IM → PDM | Package lock, mid-stage plan change
L3 | 5 working days | PDM → AP / PROJECTADMIN | Gate blocked, EIR variation needed
L4 | 10 days / next OGB | AP → OGB | Catalogue change, threshold below band
L5 | Immediate | OGB chair + SYSADMIN | Platform / security / wrong AIR live
Minimum operating procedures
ID | Procedure | Owner | Trigger
SOP-01 | Stand up a project in Atana | IM | Appointment
SOP-02 | Bind primary CDE | PROJECTADMIN | After SOP-01
SOP-03 | Generate MIDP | IM | Stage start
SOP-04 | Issue information gate | IM + PDM | Stage end
SOP-05 | Raise catalogue RFC | Steward | Change request
SOP-06 | Approve catalogue change | OGB | Monthly window
SOP-07 | Resolve ConflictRecord | IM | Ecosystem event
SOP-08 | Accept or reject AI action | Named approver | Decision raised
SOP-09 | AIM handover accept | AO + IM + FM | S6 / contract
SOP-10 | Incident — wrong AIR live | IM + TS | Defect
SOP-11 | Access review | ORGADMIN | Quarterly
SOP-12 | Audit pack export | IM | Client / ISO audit

## AI classes
AI recommendation classes — human accept required for B–F
Class | Name | Example | Approver | Auto-apply | May write SoR?
A | Inform | HVAC compliance is 71% | None (SoI) | n/a | No
B | Assign | Give D-02 Fire Rating to IA-03 | IM | No | No — assignment only
C | Plan | Generate MIDP extras for S4 | IM + PDM | No | Plan draft only, not publish
D | Gate | Block Stage 4 | IM confirms notify | Raise yes / waive no | May raise event, not waive
E | Mutate | Add Fire Rating to Door template | TS + OGB | Never | Only after accept
F | Handover | Accept AIM for D-02 | AO | Never | Only after accept

## Roadmap
Governance implementation roadmap
Wave | What | Exit criterion
G0 | Adopt this framework and name the OGB (hats may stack) | OGB named, even if two people
G1 | Object records carry Owner / Custodian / Approver | No ACTIVE catalogue with unassigned Owner
G2 | SOP-01 to SOP-04 on one live project | Stage gate pack includes RACI extract
G3 | Catalogue RFC + version pin at gates | Project cannot edit org Door template
G4 | AI accept log on Decide actions | Class E/F blocked in API without accept
G5 | Handover accept with AO / IM / FM | AIM snapshot immutable
Parked products (multi-agent, command center, twin platform, portfolio intelligence) consume these roles. They do not invent parallel ones.