## Roadmap
Wave | Window | Theme | Ships | Business value | Depends
MVP | Now | PWA planning | Wizard, engine, generated MIDP/TIDP, CDE compare, Revit JSON | IM stops retyping plans | —
v1.0 | Y0–Y1 | Platform lift | .NET 9 API, PG+RLS, Entra, generation job, workflow API | Multi-user, audit, no browser freeze | MVP freeze
v2.0 | Y1–Y2 | Operate | Catalogue pin, Fluent admin, CDE worker, Power BI views | Replayable runs, org admin | v1.0
v3.0 | Y2–Y3 | Intelligence | Read-only Copilot, My Work mobile, approved actions | Faster IM decisions | v2.0 APIs
Enterprise | Y3+ | Portfolio | DR pair region, Automate, COBie/IFC depth | Multi-region, handover | v3.0

## Prioritisation
ID | Feature | Wave | Value | Effort | Dependency risk
P1 | Extract RuleEvaluator to .NET | v1.0 | Critical | M | Low — logic exists in PWA
P2 | POST generation-runs + GET midp | v1.0 | Critical | M | Needs PG
P3 | Entra + RLS session | v1.0 | Critical | L | Identity
P4 | Workflow transition API | v1.0 | High | M | AuthZ matrix
P5 | CDE worker off UI | v1.0 | High | H | APS tokens in Key Vault
P6 | Fluent admin catalogues | v2.0 | Med | M | Don't block v1
P7 | Power BI views | v2.0 | Med | L | Replica
P8 | Copilot read tools | v3.0 | Med | H | Stable API
P9 | Full Uniclass catalogues | Park | Low now | H | Do not pull into v1
P10 | COBie / native mobile | Park | Low now | H | Enterprise

## Parking lot
Item | Why later
Asset / System / Space full Uniclass | Depth not required to generate MVP MIDP
Package mandatory library completeness | Engine + refine ticks enough
Deliverable taxonomy essay | Types already mapped to containers
ISO status/suitability UX polish | Catalogues exist in project settings
Teams / Power Automate | Needs events topic first
IFC / COBie / twin graph | After model verification API
Write-back Copilot | After read-only tools trusted
Full LOI import engine | Parse PR-IM-0002 workbook Category/Type/Attribute/DataType/Unit/Stage
Auto extract LOI columns | Map workbook columns into InformationRequirement entity
Uniclass Ss → scope package | Complete mapping beyond current tree
Uniclass SL → space mapping | Space-driven IR
Parameter inheritance | Parent system attributes cascade to children
Revit parameter mapping | Shared parameter GUID write from IR ticks
IFC property set mapping | Pset from same IR catalogue
AIR generation from LOI | Asset information requirements export
EIR generation from LOI | Exchange requirements from stage LOI
DPoW timeline view polish | Already exists; bind to IR maturity not only bars
P1 Full LOI workbook import | Parse PR-IM-0002 into ir_catalogues
P2 Scope package catalogue | Complete Ss library as SPP templates
P3 IR catalogue completeness | All teams/categories from workbook
P4 AIR | Asset information requirements from IR
P5 EIR | Exchange requirements from stage IR
P6 LOI compliance vs model | ir_observations from Revit/IFC
P7 IFC property set mapping | ifc_pset column live
P8 Revit shared parameter mapping | GUID write from IR
P9 COBie mapping | Handover from IR
P10 Digital twin mapping | Graph later
P11 IR dashboards | Compliance per team
P12 Information maturity scoring | Beyond percent
P13 Work stage information gates | Threshold config
P14 Model health scoring | MVF later
P15 Deliverable readiness scoring | IR + container state
P16 Asset Information Model (AIM) | Engine specified; productise later
P17 Asset completeness engine | Live observations vs required IR
P18 AIR generator | Export from asset_type_ir
P19 EIR generator | Stage-filtered IR export
P20 AIM dashboards | Type completeness bars
P21 Asset compliance scoring | Beyond simple percent
P22 Parameter validation engine | Datatype/unit checks
P23 Asset lifecycle requirements | PLANNED to HANDED
P24 Handover information rules | AIM acceptance
P25 Operations information rules | OIR after handover