## Cover
ATANA
Executive Command Center
KPI catalogue · scores · personas · star schema
v1.0 · 31 August 2026 · Consumes existing engines. Does not redesign them.
AIM% = present/required at LOI(stage) — same as Atana-IM-Tasks atnAimScore. Gate S4 default 95%.
Bands: Green ≥85 · Amber 70–84 · Red <70. Stage readiness Red if below gate even when other scores are green.
Power BI measure names MUST equal kpi_id. Drift versus ecc views is a defect.

## KPIs
Canonical KPIs
kpi_id | Label | Grain | Formula | Owner persona
ph | Project Health | project | 0.30 IH + 0.25 DH + 0.20 CS + 0.15 (100*(1-RISK)) + 0.10 WF | Executive, Director
poh | Portfolio Health | portfolio | Weighted average of PH | Executive, Portfolio Mgr
ih | Information Health | project | 0.15 OIR + 0.15 PIR + 0.15 EIR + 0.20 AIR + 0.20 AIM + 0.15 IDS | IM, Client
cs | Compliance | project | IDS pass / IDS required | IM
dh | Delivery Health | project | 0.40 on-time + 0.30 published + 0.30 packages clear | PDM, PM
rs | Stage Readiness | project+stage | 0.50 AIM + 0.30 published + 0.20 IDS; Red if < gate | Director
ah | Asset Health | asset | present / required at LOI | Asset Owner, FM
or | Operational Readiness | project | 0.40 AIM@LOI5 + 0.20 CMMS + 0.20 Twin + 0.20 ops docs | Ops, FM
tr | Twin Readiness | project | 0.25 identity + 0.25 IFC + 0.20 COBie + 0.20 AIM + 0.10 bind | Twin Manager
oir | OIR coverage | project | satisfied / required via graph | Client
pir | PIR coverage | project | satisfied / required | Client
eir | EIR coverage | project | satisfied / required | Client
air | AIR coverage | project | active AIR types / required by EIR | Asset Owner
aim | AIM completeness | project | present / required | Asset Owner
ids | IDS pass | project | pass / required | IM
gate | Gate threshold | project+stage | Setting (S4=95) | IM
p1 | Open P1 | project | Count | Executive
blk | Blocked packages | project | Count | PM
redn | Red projects | portfolio | Count PH<70 | Portfolio Mgr
fc_delay | Forecast delay days | project | 0.5 hist + 0.3*14*(1-RS/100) + 0.2*7*P1 | PM

## Personas
Persona → home board → alerts
Persona | Home board | Primary KPIs | Actions | Alert classes
Executive | Executive | PoH, redn, p1, oir | Open recovery, call PDM | PoH<70, P1
Asset Owner | Asset readiness | aim, air, ah | AIM accept deep-link | Asset red, AIM<gate
Client | Information | oir, pir, eir | EIR variation | EIR unmet at gate
Portfolio Manager | Portfolio | poh, redn, ih | Promote lesson | Regional red cluster
Program Manager | Portfolio filtered | ph, rs | Re-baseline info gate | Programme gate blocked
Project Director | Project | ph, rs, p1 | Gate with IM | Gate blocked
Project Manager | Project | dh, blk, fc_delay | Reassign, escalate L2 | Package BLOCKS
PDM | Project | dh, blk | Lock package | Team overload
Information Manager | Information | ih, ids, conflicts | Run IDS, resolve conflict | Conflict, IDS fail
Construction Manager | Project + Risk | rs S5, missing IR | Demand package | Missing S5 IR
Facility Manager | Asset + Twin | or, ah | Inspection / CMMS link | Fire asset red
Operations Manager | Twin + Asset | or, tr | opsWins policy | Telemetry vs AIM
Maintenance Manager | Asset | ah, missing attrs | Create WO | Missing maintain attr
Digital Twin Manager | Twin | tr components | Publish snapshot | twin id ≠ assetId

## Weights
Default score weights (ecc.score_weight version 1.0)
Score | Component | Weight
IH | OIR coverage | 15%
IH | PIR coverage | 15%
IH | EIR coverage | 15%
IH | AIR coverage | 20%
IH | AIM % | 20%
IH | IDS % | 15%
DH | On-time required deliverables | 40%
DH | Published required | 30%
DH | Packages not blocked | 30%
RS | AIM % | 50%
RS | Published required | 30%
RS | IDS % | 20%
OR | AIM % at LOI 5 | 40%
OR | CMMS bind | 20%
OR | Twin bind | 20%
OR | Ops docs published | 20%
TR | Identity on element | 25%
TR | IFC GUID | 25%
TR | COBie fields | 20%
TR | AIM % | 20%
TR | Twin bind | 10%
PH | Information Health | 30%
PH | Delivery Health | 25%
PH | Compliance | 20%
PH | 100*(1-risk_idx) | 15%
PH | Workflow throughput | 10%

## Star schema
Power BI star
Kind | Table | Grain / key
Fact | fact_project_score | project + as_of
Fact | fact_asset_score | asset + loi + as_of
Fact | fact_requirement_coverage | project + as_of
Fact | fact_deliverable_status | deliverable + as_of
Fact | fact_risk | risk + as_of
Fact | fact_forecast | project + model + as_of
Dim | dim_date | date
Dim | dim_org | org_id
Dim | dim_portfolio | portfolio_id
Dim | dim_project | project_id, weight
Dim | dim_stage | stage
Dim | dim_task_team | team_id
Dim | dim_asset_type | asset_type
Dim | dim_persona | persona
Dim | dim_score_version | score_version

## Copilot
Executive Copilot utterances
Utterance | Resolver
Show all projects at risk | PH < 70 OR P1 > 0
Which projects are behind schedule | forecast_delay_d > 0 OR DEL_ontime < 0.85
Which assets are not operationally ready | AH < gate OR OR component missing
What are the top information risks | IDS fail + unsatisfied EIR/AIR
What is causing low compliance | IDS fail grouped by template / attribute
Generate recovery plan for Stage 4 | Existing atnAnswer recover + missing list
Show OIR to AIM traceability | graph why(asset¦attr)
Which project has the highest information maturity | max IH
What is blocking Stage 4 | Existing atnAnswer block4 + RS drivers